## Advantzware Master
|  |  |  | OK = Passed Testing |  | Run | 98.45% |  |  | Location Testing : Tested in Develop
|  |  |  | Failed Testing |  | Passed | 100% |  |  | Version: 16.3.8
[6 empty] | Failed | 0%
| Tests in this color have Scripts on another sheet ( use "Note" format at top) |  |  |  |  | Blocked | 0%
Test # | Category | Sub-category | Application | Transactions Test Report | Test | Priority | Passed | Tester Name | Test Date | Failure Notes | Failure Task | Notes
101000 | Estimating | Smoke Test | EF |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-02-16
102000 | Estimating | Smoke Test | EF |  | Choose a record on first browser. Click through all tabs. Validate that there are no error messages. | 2 | Passed | John Loeb | 2017-02-16
102100 | Estimating | Add Estimate | EF |  | Add an estimate for a single item | 3 |  | John Loeb
102200 | Estimating | Add Estimate | EF |  | Add an estimate for a tandem | 3 |  | John Loeb
102300 | Estimating | Add Estimate | EF |  | Add an estimate for a set | 3 |  | John Loeb
103000 | Estimating | Smoke Test | EC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-02-16
103100 | Estimating | Smoke Test | EC |  | Choose a record on first browser. Click through all tabs. Validate that there are no error messages. | 2 |  | John Loeb
103200 | Estimating | Add Estimate | EC |  | Add an estimate for a single item | 3 |  | John Loeb
103300 | Estimating | Add Estimate | EC |  | Add an estimate for a tandem | 3 |  | John Loeb
103400 | Estimating | Add Estimate | EC |  | Add an estimate for a set | 3 |  | John Loeb
|  |  | EQ |  | Quotes |  | Passed | John Loeb
|  |  | KY |  | Kopy Estime |  | Passed | John Loeb
|  |  | ES |  | Search for Estimates |  | Passed | John Loeb
|  |  | EG |  | Global Quote Price Change |  | Passed | John Loeb
|  |  | ET |  | Tools for Sales |  | Passed | John Loeb
|  | Report | ER1 | OK = Passed Testing | Control File |  | Passed | John Loeb
|  | Report | ER2 | OK = Passed Testing | machine File |  | Passed | John Loeb
|  | Report | ER3 | OK = Passed Testing | Style File |  | Passed | John Loeb
|  | Report | ER4 | OK = Passed Testing | Prep File |  | Passed | John Loeb
|  | Report | ER5 | OK = Passed Testing | Estimates List |  | Passed | John Loeb
|  | Report | ER6 | OK = Passed Testing | Quotes List |  | Passed | John Loeb
|  | Report | ER7 | OK = Passed Testing | prep List by Mat'l Type |  | Passed | John Loeb
|  | Report | ER8 | OK = Passed Testing | Estimate by Size |  | Passed | John Loeb
|  | Report | ER9 | OK = Passed Testing | Quoted price List |  | Passed | John Loeb
|  | Report | ER10 | OK = Passed Testing | Estimates List w/margins |  | Passed | John Loeb
|  |  | EB1 |  | Machine File |  | Passed | John Loeb
|  |  | EB2 |  | Folding Styles |  | Passed | John Loeb
|  |  | EB3 |  | Corrugated Styles |  | Passed | John Loeb
|  |  | EB4 |  | Box Design |  | Passed | John Loeb
|  |  | EB5 |  | Stacking Patterns |  | Passed | John Loeb
|  |  | EB6 |  | Stacking matrix |  | Passed | John Loeb
|  |  | EB7 |  | Flute Unit Counts |  | Passed | John Loeb
|  |  | EB8 |  | Prep and Die File |  | Passed | John Loeb
|  |  | EB9 |  | Cost Estimate Control |  | Passed | John Loeb
|  |  | EB10 |  | Truck / Common Carriers |  | Passed | John Loeb
|  |  | EB11 |  | Machine Routings |  | Passed | John Loeb
|  |  | EB12 |  | Score Types |  | Passed | John Loeb
|  |  | EB13 |  | machine Attachments / Adders |  | Passed | John Loeb
104000 | Order Processing | Smoke Test | OU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
104100 | Order Processing | Smoke Test | OU1 |  | Choose a record on first browser. Click through all tabs. Validate that there are no error messages. | 2 | Passed | John Loeb
104200 | Order Processing | Add Order | OU1 |  | Add an order for a single item estimate. Validate that the order gets created with the correct information. | 3
104300 | Order Processing | Add Order | OU1 |  | Add an order for 3 items. Validate that the order gets created with all three items with the correct information. | 3 | Passed | John Loeb
105000 | Order Processing | Smoke Test | OU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
106000 | Order Processing | Smoke Test | OU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
107000 | Order Processing | Smoke Test | OU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
108000 | Order Processing | Smoke Test | OU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
109000 | Order Processing | Smoke Test | OU6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
110000 | Order Processing | Smoke Test | OU7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
111000 | Order Processing | Smoke Test | OU8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
112000 | Order Processing | Smoke Test | OU9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
113000 | Order Processing | Smoke Test | OU10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
114000 | Order Processing | Smoke Test | OU11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
115000 | Order Processing | Smoke Test | OT1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
116000 | Order Processing | Smoke Test | OT2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
117000 | Order Processing | Smoke Test | OT3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
118000 | Order Processing | Smoke Test | OT4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
119000 | Order Processing | Smoke Test | OT5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
120000 | Order Processing | Smoke Test | OS1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
121000 | Order Processing | Smoke Test | OS2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
122000 | Order Processing | Smoke Test | OS3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
123000 | Order Processing | Smoke Test | OS4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
124000 | Order Processing | Smoke Test | OS5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
125000 | Order Processing | Smoke Test | OS6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
126000 | Order Processing | Smoke Test | OS7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
127000 | Order Processing | Smoke Test | OS8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
128000 | Order Processing | Smoke Test | OB1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
129000 | Order Processing | Smoke Test | OB2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
130000 | Order Processing | Smoke Test | OB3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
131000 | Order Processing | Smoke Test | OB4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
132000 | Order Processing | Smoke Test | OB5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
133000 | Order Processing | Smoke Test | OL1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
134000 | Order Processing | Smoke Test | OL2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
135000 | Order Processing | Smoke Test | OL3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
136000 | Order Processing | Smoke Test | OC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
137000 | Order Processing | Smoke Test | OW |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
138000 | Order Processing | Smoke Test | OQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-01-16
139000 | Order Processing | Smoke Test | OQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
140000 | Order Processing | Smoke Test | OQ3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
141000 | Order Processing | Report | OR1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
142000 | Order Processing | Report | OR2 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
143000 | Order Processing | Report | OR3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
144000 | Order Processing | Report | OR4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
145000 | Order Processing | Report | OR5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
146000 | Order Processing | Report | OR6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
147000 | Order Processing | Report | OR7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
148000 | Order Processing | Report | OR8 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
149000 | Order Processing | Report | OR9 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
150000 | Order Processing | Report | OR10 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
151000 | Order Processing | Report | OR11 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
152000 | Order Processing | Report | OR12 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
153000 | Order Processing | Report | OR13 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
154000 | Order Processing | Report | OR14 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
155000 | Order Processing | Report | OR15 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
156000 | Order Processing | Report | OR16 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
157000 | Order Processing | Smoke Test | OZ1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
158000 | Order Processing | Smoke Test | OZ2 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
159000 | Order Processing | Smoke Test | OZ3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
160000 | Order Processing | Smoke Test | OZ4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
161000 | Order Processing | Smoke Test | OZ5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
162000 | Order Processing | Smoke Test | OZ6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
163000 | Order Processing | Smoke Test | OZ7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
164000 | Order Processing | Smoke Test | OZ8 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
165000 | Order Processing | Smoke Test | OZ9 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
166000 | Order Processing | Smoke Test | OF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
167000 | Order Processing | Smoke Test | OF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
168000 | Order Processing | Smoke Test | OF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
169000 | Order Processing | Smoke Test | OF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
170000 | Order Processing | Smoke Test | OF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
171000 | Order Processing | Smoke Test | OF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
172000 | Order Processing | Smoke Test | OF7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
173000 | Order Processing | Smoke Test | OF8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
174000 | Order Processing | Smoke Test | OF9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
175000 | Raw Materials | Smoke Test | MU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
176000 | Raw Materials | Smoke Test | MU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
177000 | Raw Materials | Smoke Test | MU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
178000 | Raw Materials | Smoke Test | MU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
179000 | Raw Materials | Smoke Test | MU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
180000 | Raw Materials | Smoke Test | MU6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
181000 | Raw Materials | Smoke Test | MU7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
182000 | Raw Materials | Smoke Test | MU8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
183000 | Raw Materials | Smoke Test | MC1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
184000 | Raw Materials | Smoke Test | MC2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
185000 | Raw Materials | Smoke Test | MC3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
186000 | Raw Materials | Smoke Test | MG |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
187000 | Raw Materials | Smoke Test | MQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
188000 | Raw Materials | Smoke Test | MQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
189000 | Raw Materials | Report | MR1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
190000 | Raw Materials | Report | MR2 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
191000 | Raw Materials | Report | MR3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
192000 | Raw Materials | Report | MR4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
193000 | Raw Materials | Report | MR5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
194000 | Raw Materials | Report | MR6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
195000 | Raw Materials | Report | MR7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
196000 | Raw Materials | Report | MR8 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
197000 | Raw Materials | Report | MR9 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
198000 | Raw Materials | Report | MR10 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
199000 | Raw Materials | Report | MR11 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
200000 | Raw Materials | Report | MR12 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
201000 | Raw Materials | Report | MR13 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
202000 | Raw Materials | Report | MR14 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
203000 | Raw Materials | Smoke Test | MF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
204000 | Raw Materials | Smoke Test | MF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
205000 | Raw Materials | Smoke Test | MF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
206000 | Raw Materials | Smoke Test | MF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
207000 | Raw Materials | Smoke Test | MF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
208000 | Raw Materials | Smoke Test | MF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
209000 | Finished Goods | Smoke Test | IU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
210000 | Finished Goods | Smoke Test | IU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
211000 | Finished Goods | Smoke Test | IU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
212000 | Finished Goods | Smoke Test | IU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
213000 | Finished Goods | Smoke Test | IU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
214000 | Finished Goods | Smoke Test | IU6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
215000 | Finished Goods | Smoke Test | IU7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
216000 | Finished Goods | Smoke Test | IU8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
217000 | Finished Goods | Smoke Test | IU9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
218000 | Finished Goods | Smoke Test | IC1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
219000 | Finished Goods | Smoke Test | IC2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
220000 | Finished Goods | Smoke Test | IC3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
221000 | Finished Goods | Smoke Test | IW |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
222000 | Finished Goods | Smoke Test | IQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
223000 | Finished Goods | Smoke Test | IQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
224000 | Finished Goods | Smoke Test | IR1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
225000 | Finished Goods | Smoke Test | IR2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
226000 | Finished Goods | Smoke Test | IR3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
227000 | Finished Goods | Smoke Test | IR4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
228000 | Finished Goods | Smoke Test | IR5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
229000 | Finished Goods | Smoke Test | IR6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
230000 | Finished Goods | Smoke Test | IR7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
231000 | Finished Goods | Smoke Test | IR8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
232000 | Finished Goods | Smoke Test | IR9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
233000 | Finished Goods | Smoke Test | IR10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
234000 | Finished Goods | Smoke Test | IR11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
235000 | Finished Goods | Smoke Test | IR12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
236000 | Finished Goods | Smoke Test | IR13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
237000 | Finished Goods | Smoke Test | IR14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
238000 | Finished Goods | Smoke Test | IR15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
239000 | Finished Goods | Report | IL1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
240000 | Finished Goods | Report | IL2 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
241000 | Finished Goods | Report | IL3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
242000 | Finished Goods | Report | IL4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
243000 | Finished Goods | Report | IL5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
244000 | Finished Goods | Report | IL6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
245000 | Finished Goods | Report | IL7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
246000 | Finished Goods | Report | IL8 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
247000 | Finished Goods | Report | IL9 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
248000 | Finished Goods | Report | IL10 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
249000 | Finished Goods | Report | IL11 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
250000 | Finished Goods | Report | IL12 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
251000 | Finished Goods | Report | IL13 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
252000 | Finished Goods | Report | IL14 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
253000 | Finished Goods | Report | IL15 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
254000 | Finished Goods | Smoke Test | IF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
255000 | Finished Goods | Smoke Test | IF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
256000 | Finished Goods | Smoke Test | IF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
257000 | Finished Goods | Smoke Test | IF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
258000 | Finished Goods | Smoke Test | IF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
259000 | Finished Goods | Smoke Test | IF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
260000 | Finished Goods | Smoke Test | IF7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
261000 | Sales Reports | Smoke Test | HC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
262000 | Sales Reports | Smoke Test | HB |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
263000 | Sales Reports | Smoke Test | HF |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
264000 | Sales Reports | Smoke Test | HT |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
265000 | Sales Reports | Smoke Test | HW |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
266000 | Sales Reports | Smoke Test | HZ |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
267000 | Sales Reports | Smoke Test | HV |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
268000 | Sales Reports | Smoke Test | HY |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
269000 | Sales Reports | Smoke Test | HL |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
270000 | Sales Reports | Smoke Test | HS |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
271000 | Sales Reports | Smoke Test | HM1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
| Sales Reports | Smoke Test | HM2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
| Sales Reports | Smoke Test | HM3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
| Sales Reports | Smoke Test | HM4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
| Sales Reports | Smoke Test | HM5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
| Sales Reports | Smoke Test | HM6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
272000 | Sales Reports | Report | HR1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
273000 | Sales Reports | Report | HR2 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
274000 | Sales Reports | Report | HR3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
275000 | Sales Reports | Report | HR4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
276000 | Sales Reports | Report | HR5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
277000 | Sales Reports | Report | HR6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
278000 | Sales Reports | Report | HR7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
279000 | Sales Reports | Report | HR8 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
280000 | Sales Reports | Report | HR9 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
281000 | Sales Reports | Report | HR10 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
282000 | Sales Reports | Report | HR11 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
283000 | Sales Reports | Report | HR12 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
284000 | Sales Reports | Report | HR13 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
285000 | Sales Reports | Report | HR14 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
286000 | Sales Reports | Report | HR15 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
287000 | Sales Reports | Report | HR16 | ok = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
288000 | Data Collection | Smoke Test | DU |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
289000 | Data Collection | Smoke Test | DF |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
290000 | Data Collection | Smoke Test | DL1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
291000 | Data Collection | Smoke Test | DL2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
292000 | Data Collection | Smoke Test | DL3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
293000 | Data Collection | Smoke Test | DW |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
294000 | Data Collection | Smoke Test | DT |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
295000 | Data Collection | Smoke Test | DQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
296000 | Data Collection | Smoke Test | DR1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
297000 | Data Collection | Smoke Test | DR2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
298000 | Data Collection | Smoke Test | DR3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
299000 | Data Collection | Smoke Test | DR4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
300000 | Data Collection | Smoke Test | DR5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
301000 | Data Collection | Smoke Test | DR6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
302000 | Data Collection | Smoke Test | DR7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
303000 | Data Collection | Smoke Test | DR8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
304000 | Data Collection | Smoke Test | DR9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
305000 | Data Collection | Smoke Test | DR10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
306000 | Data Collection | Smoke Test | DR11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
307000 | Data Collection | Smoke Test | DR12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
308000 | Data Collection | Smoke Test | DR13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
309000 | Data Collection | Smoke Test | DR14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
310000 | Data Collection | Smoke Test | DR15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
311000 | Data Collection | Smoke Test | DE1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
| Data Collection | Smoke Test | DE2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
313000 | Jobs | Smoke Test | JU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
314000 | Jobs | Smoke Test | JU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
315000 | Jobs | Smoke Test | JU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
316000 | Jobs | Smoke Test | JU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
317000 | Jobs | Smoke Test | JU6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
319000 | Jobs | Smoke Test | JU7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
320000 | Jobs | Smoke Test | JU8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
321000 | Jobs | Smoke Test | JC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
322000 | Jobs | Smoke Test | JQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
323000 | Jobs | Report | JR1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
324000 | Jobs | Report | JR2 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
325000 | Jobs | Report | JR3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
326000 | Jobs | Report | JR4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
327000 | Jobs | Report | JR5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
328000 | Jobs | Report | JR6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
329000 | Jobs | Report | JR7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
330000 | Jobs | Report | JR8 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
331000 | Jobs | Report | JR9 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
332000 | Jobs | Report | JR10 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
333000 | Jobs | Report | JR11 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
334000 | Jobs | Report | JR12 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
335000 | Jobs | Report | JR13 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
336000 | Jobs | Report | JR14 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
337000 | Jobs | Report | JR15 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
338000 | Jobs | Report | JL1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
339000 | Jobs | Report | JL2 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
340000 | Jobs | Report | JL3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
341000 | Jobs | Report | JL4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
342000 | Jobs | Report | JL5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
343000 | Jobs | Report | JL6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
344000 | Jobs | Report | JL7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
345000 | Jobs | Smoke Test | JF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
346000 | Jobs | Smoke Test | JF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
347000 | Jobs | Smoke Test | JF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
348000 | Jobs | Smoke Test | JF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
349000 | Jobs | Smoke Test | JF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
| Jobs | Smoke Test | JF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
350000 | Scheduler | Smoke Test | S3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
|  | Smoke Test | PU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
|  | Smoke Test | PU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
351000 | Purchasing | Smoke Test | PU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
352000 | Purchasing | Smoke Test | PU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
353000 | Purchasing | Smoke Test | PQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
354000 | Purchasing | Report | PR1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
355000 | Purchasing | Report | PR2 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
356000 | Purchasing | Report | PR3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
357000 | Purchasing | Report | PR4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
358000 | Purchasing | Report | PR5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
359000 | Purchasing | Report | PR6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
360000 | Purchasing | Report | PR7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
361000 | Purchasing | Report | PR8 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
362000 | Purchasing | Report | PR9 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
363000 | Purchasing | Report | PR10 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
364000 | Purchasing | Report | PR11 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
365000 | Purchasing | Report | PR12 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
366000 | Purchasing | Report | PR13 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
367000 | Purchasing | Report | PR14 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
368000 | Purchasing | Smoke Test | PF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
369000 | Purchasing | Smoke Test | PF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
370000 | Receivables | Smoke Test | AU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
371000 | Receivables | Smoke Test | AU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
372000 | Receivables | Smoke Test | AU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
373000 | Receivables | Smoke Test | AU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
374000 | Receivables | Smoke Test | AU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
375000 | Receivables | Smoke Test | AW1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
376000 | Receivables | Smoke Test | AW2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
377000 | Receivables | Smoke Test | AW3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
378000 | Receivables | Smoke Test | AW4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
379000 | Receivables | Smoke Test | AC1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
380000 | Receivables | Smoke Test | AC2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
381000 | Receivables | Smoke Test | AC3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
382000 | Receivables | Smoke Test | AC4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
383000 | Receivables | Smoke Test | AC5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
384000 | Receivables | Smoke Test | AC6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
385000 | Receivables | Smoke Test | AC7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
386000 | Receivables | Smoke Test | AC8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
387000 | Receivables | Smoke Test | AB |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
388000 | Receivables | Smoke Test | AQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
389000 | Receivables | Smoke Test | AQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
390000 | Receivables | Smoke Test | AQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
391000 | Receivables | Smoke Test | AQ3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
392000 | Receivables | Smoke Test | AQ4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
393000 | Receivables | Smoke Test | AQ5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
394000 | Receivables | Smoke Test | AR1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
395000 | Receivables | Smoke Test | AR2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
396000 | Receivables | Smoke Test | AR3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
397000 | Receivables | Smoke Test | AR4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
398000 | Receivables | Smoke Test | AR5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
399000 | Receivables | Smoke Test | AR6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
400000 | Receivables | Smoke Test | AR7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
401000 | Receivables | Smoke Test | AR8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
402000 | Receivables | Smoke Test | AR9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
403000 | Receivables | Smoke Test | AR10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
404000 | Receivables | Smoke Test | AR11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
405000 | Receivables | Smoke Test | AR12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
406000 | Receivables | Smoke Test | AR13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
407000 | Receivables | Smoke Test | AR14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
408000 | Receivables | Smoke Test | AR15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
409000 | Receivables | Smoke Test | AR16 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
410000 | Receivables | Smoke Test | AL1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
411000 | Receivables | Smoke Test | AL2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
412000 | Receivables | Smoke Test | AL3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
413000 | Receivables | Smoke Test | AF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
414000 | Receivables | Smoke Test | AF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
415000 | Receivables | Smoke Test | AF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
416000 | Receivables | Smoke Test | AF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
417000 | Receivables | Smoke Test | AF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
418000 | Receivables | Smoke Test | AF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
419000 | Receivables | Smoke Test | AF7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
420000 | Receivables | Smoke Test | AF8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
421000 | Payables | Smoke Test | VU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
422000 | Payables | Smoke Test | VU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
423000 | Payables | Smoke Test | VU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
424000 | Payables | Smoke Test | AW1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
425000 | Payables | Smoke Test | AW2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
426000 | Payables | Smoke Test | VB1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
427000 | Payables | Smoke Test | VB2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
428000 | Payables | Smoke Test | VB3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
429000 | Payables | Smoke Test | VC1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
430000 | Payables | Smoke Test | VC2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
431000 | Payables | Smoke Test | VC3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
432000 | Payables | Smoke Test | VC4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
433000 | Payables | Smoke Test | VC5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
434000 | Payables | Smoke Test | VT1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
435000 | Payables | Smoke Test | VT2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
436000 | Payables | Smoke Test | VT3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
437000 | Payables | Smoke Test | VT4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
438000 | Payables | Smoke Test | VL1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
439000 | Payables | Smoke Test | VL2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
440000 | Payables | Smoke Test | VL3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
441000 | Payables | Smoke Test | VQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
442000 | Payables | Smoke Test | VQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
443000 | Payables | Smoke Test | VQ3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
444000 | Payables | Smoke Test | VQ4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
445000 | Payables | Report | VR1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
446000 | Payables | Report | VR2 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
447000 | Payables | Report | VR3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
448000 | Payables | Report | VR4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
449000 | Payables | Report | VR5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
450000 | Payables | Report | VR6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
451000 | Payables | Report | VR7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
452000 | Payables | Report | VR8 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
453000 | Payables | Report | VR9 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
454000 | Payables | Report | VR10 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
455000 | Payables | Report | VR11 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
456000 | Payables | Report | VR12 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
457000 | Payables | Report | VR13 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
458000 | Payables | Report | VR14 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
459000 | Payables | Report | VR15 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
460000 | Payables | Smoke Test | VF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
461000 | Payables | Smoke Test | VF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
462000 | Payables | Smoke Test | VF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
463000 | Payables | Smoke Test | VF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
464000 | Payables | Smoke Test | VF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
465000 | Payables | Smoke Test | VF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
| Payables | Smoke Test | VF7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
466000 | General Ledger | Smoke Test | GU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
467000 | General Ledger | Smoke Test | GU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
468000 | General Ledger | Smoke Test | GU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
469000 | General Ledger | Smoke Test | GU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
470000 | General Ledger | Smoke Test | GU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
471000 | General Ledger | Smoke Test | GC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
472000 | General Ledger | Smoke Test | GY |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
473000 | General Ledger | Smoke Test | GT |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
474000 | General Ledger | Smoke Test | GW1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
475000 | General Ledger | Smoke Test | GW2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
476000 | General Ledger | Smoke Test | GW3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
477000 | General Ledger | Smoke Test | GQ |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
478000 | General Ledger | Smoke Test | GR1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
479000 | General Ledger | Report | GR1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
| General Ledger | Report | GR2 | OK = Passed Testing | Launch without error message and review basic functionality |  | Passed | John Loeb
480000 | General Ledger | Report | GR3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
481000 | General Ledger | Report | GR4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
482000 | General Ledger | Report | GR5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
483000 | General Ledger | Report | GR6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
484000 | General Ledger | Report | GR7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
485000 | General Ledger | Report | GR8 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
486000 | General Ledger | Report | GR9 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb
487000 | General Ledger | Smoke Test | GF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
488000 | General Ledger | Smoke Test | GF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
489000 | General Ledger | Smoke Test | GF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
490000 | General Ledger | Smoke Test | GF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
491000 | General Ledger | Smoke Test | GF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
492000 | General Ledger | Smoke Test | GF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
493000 | System | Smoke Test | NL1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
494000 | System | Smoke Test | NL2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
495000 | System | Smoke Test | NF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
496000 | System | Smoke Test | NF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
497000 | System | Smoke Test | NF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
498000 | System | Smoke Test | NF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
499000 | System | Smoke Test | NF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
500000 | System | Smoke Test | NF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
501000 | System | Smoke Test | NF7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
502000 | System | Smoke Test | NF8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
503000 | System | Smoke Test | NF9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
504000 | System | Smoke Test | BF10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
505000 | System | Smoke Test | NF11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
506000 | System | Smoke Test | NF12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
507000 | System | Smoke Test | NF13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
508000 | System | Smoke Test | NF14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
509000 | System | Smoke Test | NF15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
510000 | System | Smoke Test | NY1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
511000 | System | Smoke Test | NY2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
512000 | System | Smoke Test | NY3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
513000 | System | Smoke Test | NY4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
514000 | System | Smoke Test | NY5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
515000 | System | Smoke Test | NY6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
516000 | System | Smoke Test | NY7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
517000 | System | Smoke Test | NY8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
518000 | System | Smoke Test | NY9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
519000 | System | Smoke Test | NY10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
520000 | System | Smoke Test | NY11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
521000 | System | Smoke Test | NY12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
522000 | System | Smoke Test | NY13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
523000 | System | Smoke Test | NY14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
524000 | System | Smoke Test | NY15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
525000 | System | Smoke Test | NU |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
526000 | System | Smoke Test | NC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
527000 | System | Smoke Test | NB |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
528000 | System | Smoke Test | NK1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
529000 | System | Smoke Test | NK2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
530000 | System | Smoke Test | NK3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
| System | Smoke Test | NK4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
| System | Smoke Test | NK5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
531000 | System | Smoke Test | NR |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
532000 | System | Smoke Test | NT |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
533000 | System | Smoke Test | NQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
534000 | System | Smoke Test | NQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
535000 | System | Smoke Test | NQ3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
536000 | System | Smoke Test | NQ4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
537000 | System | Smoke Test | NQ5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
538000 | System | Smoke Test | NQ6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
539000 | System | Smoke Test | NQ7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
540000 | System | Smoke Test | NQ8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
541000 | System | Smoke Test | NQ9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
542000 | System | Smoke Test | NQ10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
543000 | System | Smoke Test | NQ11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
544000 | System | Smoke Test | NQ12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
545000 | System | Smoke Test | NQ13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
546000 | System | Smoke Test | NQ14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
547000 | System | Smoke Test | NQ15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
548000 | System | Smoke Test | NQ16 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
549000 | System | Smoke Test | NW |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb
550000 | System | Smoke Test | NZ1 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb
551000 | System | Smoke Test | NZ2 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb
552000 | System | Smoke Test | NZ3 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb
553000 | System | Smoke Test | NZ4 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb
554000 | System | Smoke Test | NZ5 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb
555000 | System | Smoke Test | NZ6 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb
556000 | System | Smoke Test | NZ7 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb
557000 | System | Smoke Test | NZ8 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb
558000 | System | Smoke Test | NZ9 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb
559000 | System | Smoke Test | NZ10 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb
| System | Smoke Test | NZ11 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb
| System | Smoke Test | NZ12 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb
560000 | System | Smoke Test | NR1 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb
561000 | System | Smoke Test | NR2 |  | Launch without error message and review basic functionality | 99 | Passed | John Loeb
562000 | System | Smoke Test | NR3 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb
563000 | System | Smoke Test | NR4 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb
564000 | System | Smoke Test | NR5 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb
565000 | System | Smoke Test | Exit |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb

## Advantzware Add-ons
[6 empty] | Run | 125.7%
| Addons - Testing |  |  |  |  | Passed | 81.75%
[6 empty] | Failed | 18.25%
| Tests in this color have Scripts on another sheet ( use "Note" format at top) |  |  |  |  | Blocked | 0%
Test # | Category | Sub-category | Application | Time Speed | Test | Priority | Passed | Tester Name | Test Date | Failure Notes | Failure Task | Notes
101000 | Touch Screen Menu | Smoke Test | TD |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-10-06
102000 | Touch Screen Posting | Smoke Test | TP |  | Post Touch Data to ASI Database | 1 | Passed | John Loeb | 2016-10-06
102100 | Report | Smoke Test | TR1 |  | Daily Summary by Employee | 1 | Passed | John Loeb | 2016-10-06
102200 | Report | Smoke Test | TR2 |  | Employees List | 1 | Passed | John Loeb | 2016-10-06
102300 | Report | Smoke Test | TR3 |  | Machine Transaction List | 1 | Passed | John Loeb | 2016-10-06
103000 | Report | Smoke Test | TR4 |  | Complete Machine Jobs List | 1 | Passed | John Loeb | 2016-10-06
103100 | Report | Smoke Test | TR5 |  | Shifts List | 1 | Passed | John Loeb | 2016-10-06
103200 | Report | Smoke Test | TR6 |  | Machine Assigned Chrg Cds List | 1 | Passed | John Loeb | 2016-10-06
103300 | Report | Smoke Test | TR7 |  | Machine Assigned Shifts List | 1 | Passed | John Loeb | 2016-10-06
103400 | Report | Smoke Test | TR8 |  | Employee Types List | 1 | Passed | John Loeb | 2016-10-06
| Report | Smoke Test | TR9 |  | Labor Report | 1 | Passed | John Loeb | 2016-10-06
| Report | Smoke Test | TR10 |  | Employee Time by Job and Machine | 1 | Passed | John Loeb | 2016-10-06
| Report | Smoke Test | TR11 |  | In/Out Transaction Report | 1 | Passed | John Loeb | 2016-10-06
| Report | Smoke Test | TR12 |  | Employee Time Sheet | 1 | Passed | John Loeb | 2016-10-06
| Report | Smoke Test | TR13 |  | Unreported Labor Report | 1 | Passed | John Loeb | 2016-10-06
| Report | Smoke Test | TR14 |  | Machinen Notes Report | 1 | Passed | John Loeb | 2016-10-06
|  |  | TD |  |  | 1 | Passed | John Loeb | 2016-10-21
|  |  | TP |  |  | 1 | Passed | John Loeb | 2016-10-21
|  |  | TR1 |  |  | 1 | Passed | John Loeb | 2016-10-21
|  |  | TR2 |  |  | 1 | Passed | John Loeb | 2016-10-21
|  |  | TR3 |  |  | 1 | Passed | John Loeb | 2016-10-21
|  |  | TR4 |  |  | 1 | Passed | John Loeb | 2016-10-21
|  |  | TR5 |  |  | 1 | Passed | John Loeb | 2016-10-21
|  |  | TR6 |  |  | 1 | Passed | John Loeb | 2017-01-16
|  |  | TR7 |  |  | 1 | Passed | John Loeb
|  |  | TR8 |  |  | 1 | Passed | John Loeb
|  |  | TR9 |  |  | 1 | Passed | John Loeb
|  |  | TR10 |  |  | 1 | Passed | John Loeb
|  |  | TR11 |  |  | 1 | Passed | John Loeb
|  |  | TR12 |  |  | 1 | Passed | John Loeb
|  |  | TR13 |  |  | 1 | Passed | John Loeb
|  |  | TR14 |  |  | 1 | Passed | John Loeb
| Employee Tracking | Smoke Test | TF1 |  | Employees | 1 | Failed | John Loeb
|  | Smoke Test | TF2 |  | Employee Transaction Summary | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | TF3 |  | Machine Transactions | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | TF4 |  | Employee Transactions | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | TF5 |  | Completed Machine Jobs | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | TF6 |  | Job Sequence | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | TF7 |  | Shifts | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | TF8 |  | Machine Assigned Charge Codes | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | TF9 |  | Machine Assigned Shifts | 1 | Passed | John Loeb | 2016-10-06
|  |  | TF2 |  |  | 1 | Passed | John Loeb
|  |  | TF3 |  |  | 1 | Passed | John Loeb
|  |  | TF4 |  |  | 1 | Passed | John Loeb
|  |  | TF5 |  |  | 1 | Passed | John Loeb
|  |  | TF6 |  |  | 1 | Passed | John Loeb
|  |  | TF7 |  |  | 1 | Passed | John Loeb
|  |  | TF8 |  |  | 1 | Passed | John Loeb
|  |  | TF9 |  |  | 1 | Passed | John Loeb
|  |  | TF10 |  |  | 1 | Failed | John Loeb
|  |  | TF11 |  |  | 1 | Passed | John Loeb
|  |  | TF12 |  |  | 1 | Passed | John Loeb
|  |  | TF13 |  |  | 1 | Passed | John Loeb
|  |  | TF14 |  |  | 1 | Passed | John Loeb
|  |  | TF15 |  |  | 1 | Passed | John Loeb
|  |  | SM |  |  |  | Passed
|  | Smoke Test | TF1B |  | Employee Default Rates | 1 |  | John Loeb
|  | Smoke Test | TF11 |  | Employee Types | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | TF12 |  | RePost Touch Data to ASI Database | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | TF13 |  | Purge Employee Transaction | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | TF14 |  | Purge Touch Data | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | TF15 |  | Purge Zero Time Transaction | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | TF1A |  | Purge Zero Time Transaction | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | SM |  | Materials | 1 | Passed | John Loeb | 2016-10-06
| Material Menu | Smoke Test | SM-1 |  | Receive Material | 1 | Passed | John Loeb | 2016-10-06
| Material Menu | Smoke Test | SM-2 |  | Issue Material | 1 | Passed | John Loeb | 2016-10-06
| Material Menu | Smoke Test | SM-3 |  | Job Returns | 1 | Passed | John Loeb | 2016-10-06
| Material Menu | Smoke Test | SM-4 |  | Transfer Material | 1 | Passed | John Loeb | 2016-10-06
| Material Menu | Smoke Test | SM-5 |  | Move Materials | 1 | Passed | John Loeb | 2016-10-06
| Material Menu | Smoke Test | SM-6 |  | Count Material | 1 | Passed | John Loeb | 2016-10-06
| Material Menu | Smoke Test | SM-7 |  | Delete Material | 1 | Passed | John Loeb | 2016-10-06
| Material Menu | Smoke Test | SM-8 |  | Post Material | 1 | Passed | John Loeb | 2016-10-06
| Material Menu | Smoke Test | SM-9 |  | Scan Vendor Tag | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | SF |  | Finished Goods | 1 | Passed | John Loeb | 2016-10-06
| FG Warehouse | Smoke Test | SF-1 |  | Receive Goods | 1 | Passed | John Loeb | 2016-10-06
| FG Warehouse | Smoke Test | SF-2 |  | Move receipts | 1 | Passed | John Loeb | 2016-10-06
| FG Warehouse | Smoke Test | SF-3 |  | Transfer Goods | 1 | Passed | John Loeb | 2016-10-06
| FG Warehouse | Smoke Test | SF-4 |  | Count Goods | 1 | Passed | John Loeb | 2016-10-06
| FG Warehouse | Smoke Test | SF-5 |  | Delete Goods | 1 | Passed | John Loeb | 2016-10-06
| FG Warehouse | Smoke Test | SF-6 |  | Return Goods | 1 | Passed | John Loeb | 2016-10-06
| FG Warehouse | Smoke Test | SF-7 |  | Post Goods | 1 | Passed | John Loeb | 2016-10-06
| FG Warehouse | Smoke Test | SF-8 |  | Consolidate Tags | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | SB |  | Bill of Lading Transaction | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | SB1 |  | Create BOL | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | SB2 |  | Update Release | 1 | Passed | John Loeb | 2016-10-06
|  | p | SL |  | Label Menu | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | SL1 |  | Make FG Load Tags | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | SL2 |  | Make Raw Mat' Tags | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | SL3 |  | Scan Case Labels | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | SL4 |  | Make WIP Tags | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | SL5 |  | File Maintenance | 1 | Passed | John Loeb | 2016-10-06
|  | Smoke Test | SR1 |  | Production Report | 1% | Passed | John Loeb | 2016-10-06
|  | Smoke Test | MP |  | Prospects and Customers Names | 1 | Passed | John Loeb | 2016-10-06
104000 |  | Smoke Test | ML |  | List Management | 1 | Passed | John Loeb | 2016-10-06
104100 |  | Smoke Test | MR1 |  | Contact List | 1 | Passed | John Loeb | 2016-10-06
104200 |  | Smoke Test | MR2 |  | Mail List Merge | 1 | Passed | John Loeb | 2016-10-06
104300 |  | Smoke Test | MR3 |  | Mail List Label | 1 | Passed | John Loeb | 2016-10-06
105000 |  | Smoke Test | MF1 |  | Copy Customers to Contact Mgr. | 1 | Passed | John Loeb | 2016-10-06
106000 |  | Smoke Test | MF2 |  | Download to Laptop | 1 | Passed | John Loeb | 2016-10-06
107000 |  | Smoke Test | MF3 |  | Upload to Server | 1 | Passed | John Loeb | 2016-10-06
108000 |  | Smoke Test | QR |  | Request For Quotes | 1 | Passed | John Loeb
109000 |  | Smoke Test | QL1 |  | Single RFQ List | 1 | Passed | John Loeb | 2016-10-06
110000 |  | Smoke Test | QL2 |  | RFQ List | 1 | Passed | John Loeb | 2016-10-06
111000 |  | Smoke Test | QF1 |  | RFQ File Maintenance | 1 | Passed | John Loeb | 2016-10-06
112000 |  | Smoke Test | WD1 |  | Item Receipt | 1 | Passed | John Loeb | 2016-10-06
113000 |  | Smoke Test | WD2 |  | Item Usage | 1 | Passed | John Loeb | 2016-10-06
114000 |  | Smoke Test | WR1 |  | Customer Inventory Report 1 | 1 | Passed | John Loeb | 2016-10-06
115000 |  | Smoke Test | WR2 |  | Customer Inventory Report 2 | 1 | Passed | John Loeb | 2016-10-06
116000 |  | Smoke Test | WR3 |  | Red Flag Report | 1 | Passed | John Loeb | 2016-10-06
117000 |  | Smoke Test | WR4 |  | Exception Report | 1 | Passed | John Loeb | 2016-10-06
118000 |  | Smoke Test | WF1 |  | Item File Maintenance | 1 | Passed | John Loeb | 2016-10-06
119000 |  | Smoke Test | WF2 |  | Plant File Maintenance | 1 | Passed | John Loeb | 2016-10-06
120000 |  | Smoke Test | WF3 |  | Vendor Cross reference | 1 | Passed | John Loeb | 2016-10-06
121000 |  | Smoke Test | WF4 |  | Warehouse History | 1 | Passed | John Loeb | 2016-10-06
122000 |  | Smoke Test | WF5 |  | Customer Inventory | 1 | Passed | John Loeb | 2016-10-06
123000 |  | Smoke Test | EI |  | Inbound Processing | 1 |  | John Loeb
124000 |  | Smoke Test | EO |  | Outbound Processing | 1 |  | John Loeb
125000 |  | Smoke Test | EB1 |  | Document Controls | 1 | Failed | John Loeb
126000 |  | Smoke Test | EB2 |  | Purchase Orders (850) | 1 | Failed | John Loeb
127000 |  | Smoke Test | EB3 |  | Invoices (810) | 1 | Failed | John Loeb
128000 |  | Smoke Test | EB4 |  | Ship Notes (856) | 1 | Failed | John Loeb
129000 |  | Smoke Test | EB5 |  | sales Analysis (852) | 1 | Failed | John Loeb
130000 |  | Smoke Test | EB6 |  | Product catalog (832) | 1 | Failed | John Loeb
131000 |  | Smoke Test | EB7 |  | Organization (816) | 1 | Failed | John Loeb
132000 |  | Smoke Test | EF1 |  | Trading Partners | 1 | Failed | John Loeb
133000 |  | Smoke Test | EF2 |  | Transaction Sets | 1 | Failed | John Loeb
134000 |  | Smoke Test | EF3 |  | Ship-to Locations | 1 | Failed | John Loeb
135000 |  | Smoke Test | EF4 |  | Customer Items | 1 | Failed | John Loeb
136000 |  | Smoke Test | EF5 |  | Wa / SCAC Codes | 1 | Failed | John Loeb
137000 |  | Smoke Test | EF6 |  | Controls | 1 | Failed | John Loeb
138000 |  | Smoke Test | ER1 |  | Document Controls | 1 | Failed | John Loeb
139000 |  | Smoke Test | ER2 |  | Purchase Orders (850) | 1 | Failed | John Loeb
140000 |  | Smoke Test | ER3 |  | Invoices (810) | 1 | Failed | John Loeb
141000 |  | Smoke Test | ER4 |  | Ship Notices (856) | 1 | Failed | John Loeb
142000 |  | Smoke Test | ER5 |  | Sales Analysis (852) | 1 | Failed | John Loeb
143000 |  | Smoke Test | ER6 |  | Product catalog (832) | 1 | Failed | John Loeb
144000 |  | Smoke Test | ER7 |  | Organization (816) | 1 | Failed | John Loeb
145000 |  | Smoke Test | ER8 |  | Trading Partners | 1 | Failed | John Loeb
146000 |  | Smoke Test | EP1 |  | Purge Documents | 1 | Failed | John Loeb
147000 |  | Smoke Test | EP2 |  | Edit Error Codes | 1 | Failed | John Loeb
148000
149000
150000
151000
152000
153000
154000
155000
156000
157000
158000
159000
160000
161000
162000
163000
164000
165000
166000
167000
168000
169000
170000
171000
172000
173000
174000
175000
176000
177000
178000
179000
180000
181000
182000
183000
184000
185000
186000
187000
188000
189000
190000
191000
192000
193000
194000
195000
196000
197000
198000
199000
200000
201000
202000
203000
204000
205000
206000
207000
208000
209000
210000
211000
212000
213000
214000
215000
216000
217000
218000
219000
220000
221000
222000
223000
224000
225000
226000
227000
228000
229000
230000
231000
232000
233000
234000
235000
236000
237000
238000
239000
240000
241000
242000
243000
244000
245000
246000
247000
248000
249000
250000
251000
252000
253000
254000
255000
256000
257000
258000
259000
260000 | [11 empty] | Tabs Info not right
261000
262000
263000
264000
265000
266000
267000
268000
269000
270000
271000
272000
273000
274000
275000
276000
277000
278000
279000
280000
281000
282000
283000
284000
285000
286000
287000
288000
289000
290000
291000
292000
293000
294000
295000
296000
297000
298000
299000
300000
301000
302000
303000
304000
305000
306000
307000
308000
309000
310000
311000
312000
313000
314000
315000
316000
317000
319000
320000
321000
322000
323000
324000
325000
326000
327000
328000
329000
330000
331000
332000
333000
334000
335000
336000
337000
338000
339000
340000
341000
342000
343000
344000
345000
346000
347000
348000
349000
350000
351000
352000
353000
354000
355000
356000
357000
358000
359000
360000
361000
362000
363000
364000
365000
366000
367000
368000
369000
370000
371000
372000
373000
374000
375000
376000
377000
378000
379000
380000
381000
382000
383000
384000
385000
386000
387000
388000
389000
390000
391000
392000
393000
394000
395000
396000
397000
398000
399000
400000
401000
402000
403000
404000
405000
406000
407000
408000
409000
410000
411000
412000
413000
414000
415000
416000
417000
418000
419000
420000
421000
422000
423000
424000
425000
426000
427000
428000
429000
430000
431000
432000
433000
434000
435000
436000
437000
438000
439000
440000
441000
442000
443000
444000
445000
446000
447000
448000
449000
450000
451000
452000
453000
454000
455000
456000
457000
458000
459000
460000
461000
462000
463000
464000
465000
466000
467000
468000
469000
470000
471000
472000
473000
474000
475000
476000
477000
478000
479000
480000
481000
482000
483000
484000
485000
486000
487000
488000
489000
490000
491000
492000
493000
494000
495000
496000
497000
498000
499000
500000
501000
502000
503000
504000
505000
506000
507000
508000
509000
510000
511000
512000
513000
514000
515000
516000
517000
518000
519000
520000
521000
522000
523000
524000
525000
526000
527000
528000
529000
530000
531000
532000
533000
534000
535000
536000
537000
538000
539000
540000
541000
542000
543000
544000
545000
546000
547000
548000
549000
550000
551000
552000
553000
554000
555000
556000
557000
558000
559000
560000
561000
562000
563000
564000
565000

## Test Scripts - Estimating
v Use this filter to find the test
Script ID | Test # | Step # | Action | Expected Result | Actual Result (blank if Expected Result met) | Passed?
102100-01 | 102100 | 1
102100-02 | 102100 | 2
102100-03 | 102100 | 3
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00

## Test Scripts - Order Processing
v Use this filter to find the test
Script ID | Test # | Step # | Action | Expected Result | Actual Result (blank if Expected Result met) | Passed?
102100-01 | 102100 | 1
102100-02 | 102100 | 2
102100-03 | 102100 | 3
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00

## Test Data
Data Type | Data ID | Data Description
Estimate |  | Existing Single Item Estimate - Corrugated
Estimate |  | Existing Set Estimate - Corrugated
Order
BOL
OE Invoice
AR Invoice
Release
Job