## Advantzware Master
|  |  |  | OK = Passed Testing |  | Run | 100% |  |  | Location Testing : Tested in Develop
|  |  |  | Failed Testing |  | Passed | 0% |  |  | Version: 17.0.0
[6 empty] | Failed | 0% |  |  | AWS - Testing Site
| Tests in this color have Scripts on another sheet ( use "Note" format at top) |  |  |  |  | Blocked | 0% |  |  | Classic Mode
Test # | Category | Sub-category | Application | Transactions Test Report | Test | Priority | Passed | Tester Name | Test Date | Failure Notes | Failure Task | Notes
101000 | Estimating | Smoke Test | EF |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2017-04-17 | Prep./Rout Tab - Canot get on query br_table which is not opened (3159) - Also on the Quantities tab
|  | Smoke Test | F3 |  | Check F3 Lookup |  | Passed | John Loeb | 2017-04-17
102000 | Estimating | Smoke Test | EF |  | Choose a record on first browser. Click through all tabs. Validate that there are no error messages. | 2 | Failed | John Loeb | 2017-04-17 | Prep./Rout Tab - Canot get on query br_table which is not opened (3159) - Also on the Quantities tab
102100 | Estimating | Add Estimate | EF |  | Add an estimate for a single item | 3 |  | John Loeb
102200 | Estimating | Add Estimate | EF |  | Add an estimate for a tandem | 3 |  | John Loeb
102300 | Estimating | Add Estimate | EF |  | Add an estimate for a set | 3 |  | John Loeb
103000 | Estimating | Smoke Test | EC |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2017-04-17 | Prep./Rout Tab - Canot get on query br_table which is not opened (3159)
103100 | Estimating | Smoke Test | EC |  | Choose a record on first browser. Click through all tabs. Validate that there are no error messages. | 2 | Failed | John Loeb | 2017-04-17 | Prep./Rout Tab - Canot get on query br_table which is not opened (3159)
103200 | Estimating | Add Estimate | EC |  | Add an estimate for a single item | 3 |  | John Loeb
103300 | Estimating | Add Estimate | EC |  | Add an estimate for a tandem | 3 |  | John Loeb
103400 | Estimating | Add Estimate | EC |  | Add an estimate for a set | 3 |  | John Loeb
|  |  | EQ |  | Quotes |  | Passed | John Loeb | 2017-04-17
|  |  | KY |  | Kopy Estime |  | Passed | John Loeb | 2017-04-17
|  |  | ES |  | Search for Estimates |  | Passed | John Loeb | 2017-04-17
|  |  | EG |  | Global Quote Price Change |  | Passed | John Loeb | 2017-04-17
|  |  | ET |  | Tools for Sales |  | Passed | John Loeb | 2017-04-17
|  | Report | ER1 | OK = Passed Testing | Control File |  | Passed | John Loeb | 2017-04-17
|  | Report | ER2 | OK = Passed Testing | machine File |  | Passed | John Loeb | 2017-04-17
|  | Report | ER3 | OK = Passed Testing | Style File |  | Passed | John Loeb | 2017-04-17
|  | Report | ER4 | OK = Passed Testing | Prep File |  | Passed | John Loeb | 2017-04-17
|  | Report | ER5 | OK = Passed Testing | Estimates List |  | Passed | John Loeb | 2017-04-17
|  | Report | ER6 | OK = Passed Testing | Quotes List |  | Passed | John Loeb | 2017-04-17
|  | Report | ER7 | OK = Passed Testing | prep List by Mat'l Type |  | Passed | John Loeb | 2017-04-17
|  | Report | ER8 | OK = Passed Testing | Estimate by Size |  | Passed | John Loeb | 2017-04-17
|  | Report | ER9 | OK = Passed Testing | Quoted price List |  | Passed | John Loeb | 2017-04-17
|  | Report | ER10 | OK = Passed Testing | Estimates List w/margins |  | Passed | John Loeb | 2017-04-17
|  |  | EB1 |  | Machine File |  | Passed | John Loeb | 2017-04-17
|  |  | EB2 |  | Folding Styles |  | Passed | John Loeb | 2017-04-17
|  |  | EB3 |  | Corrugated Styles |  | Failed | John Loeb | 2017-04-17 | Routing Tab - Cannot get on query br_table which is not opened (3159)
|  |  | EB4 |  | Box Design |  | Passed | John Loeb | 2017-04-17
|  |  | EB5 |  | Stacking Patterns |  | Passed | John Loeb | 2017-04-17
|  |  | EB6 |  | Stacking matrix |  | Failed | John Loeb | 2017-04-17 | Cannot Get on guery br_table which is not opened (3159)
|  |  | EB7 |  | Flute Unit Counts |  | Passed | John Loeb | 2017-04-17
|  |  | EB8 |  | Prep and Die File |  | Passed | John Loeb | 2017-04-17
|  |  | EB9 |  | Cost Estimate Control |  | Passed | John Loeb | 2017-04-17
|  |  | EB10 |  | Truck / Common Carriers |  | Passed | John Loeb | 2017-04-17
|  |  | EB11 |  | Machine Routings |  | Passed | John Loeb | 2017-04-17
|  |  | EB12 |  | Score Types |  | Passed | John Loeb | 2017-04-17
|  |  | EB13 |  | Machine Attachments / Adders |  | Passed | John Loeb | 2017-04-17
|  |  | Eb14 |  | markup Matrix |  | Passed | John Loeb | 2017-04-17
104000 | Order Processing | Smoke Test | OU1 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2017-04-17 | Items Tab - Cannot Get on guery br_table which is not opened (3159) - Also the prep /Route Tab
104100 | Order Processing | Smoke Test | OU1 |  | Choose a record on first browser. Click through all tabs. Validate that there are no error messages. | 2 | Failed | John Loeb | 2017-04-17 | Items Tab - Cannot Get on guery br_table which is not opened (3159) - Also the prep /Route Tab
104200 | Order Processing | Add Order | OU1 |  | Add an order for a single item estimate. Validate that the order gets created with the correct information. | 3 |  |  | 2017-04-17
104300 | Order Processing | Add Order | OU1 |  | Add an order for 3 items. Validate that the order gets created with all three items with the correct information. | 3 |  | John Loeb
105000 | Order Processing | Smoke Test | OU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
106000 | Order Processing | Smoke Test | OU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
107000 | Order Processing | Smoke Test | OU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
108000 | Order Processing | Smoke Test | OU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
109000 | Order Processing | Smoke Test | OU6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
110000 | Order Processing | Smoke Test | OU7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
111000 | Order Processing | Smoke Test | OU8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
112000 | Order Processing | Smoke Test | OU9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
113000 | Order Processing | Smoke Test | OU10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
114000 | Order Processing | Smoke Test | OU11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
115000 | Order Processing | Smoke Test | OT1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
116000 | Order Processing | Smoke Test | OT2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
117000 | Order Processing | Smoke Test | OT3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
118000 | Order Processing | Smoke Test | OT4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
119000 | Order Processing | Smoke Test | OT5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
120000 | Order Processing | Smoke Test | OS1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
121000 | Order Processing | Smoke Test | OS2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
122000 | Order Processing | Smoke Test | OS3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
123000 | Order Processing | Smoke Test | OS4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
124000 | Order Processing | Smoke Test | OS5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
125000 | Order Processing | Smoke Test | OS6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
126000 | Order Processing | Smoke Test | OS7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
127000 | Order Processing | Smoke Test | OS8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
128000 | Order Processing | Smoke Test | OB1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
129000 | Order Processing | Smoke Test | OB2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
130000 | Order Processing | Smoke Test | OB3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
131000 | Order Processing | Smoke Test | OB4 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2017-04-17 | starting posting substring, overlay
132000 | Order Processing | Smoke Test | OB5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
133000 | Order Processing | Smoke Test | OL1 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2017-04-17 | Cannot Get on guery br_table which is not opened (3159)
134000 | Order Processing | Smoke Test | OL2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
135000 | Order Processing | Smoke Test | OL3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
136000 | Order Processing | Smoke Test | OC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
137000 | Order Processing | Smoke Test | OW |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
138000 | Order Processing | Smoke Test | OQ1 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2017-04-17 | Est Tab - Error message
139000 | Order Processing | Smoke Test | OQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
140000 | Order Processing | Smoke Test | OQ3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
141000 | Order Processing | Report | OR1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
142000 | Order Processing | Report | OR2 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
143000 | Order Processing | Report | OR3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
144000 | Order Processing | Report | OR4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
145000 | Order Processing | Report | OR5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
146000 | Order Processing | Report | OR6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
147000 | Order Processing | Report | OR7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
148000 | Order Processing | Report | OR8 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
149000 | Order Processing | Report | OR9 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
150000 | Order Processing | Report | OR10 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
151000 | Order Processing | Report | OR11 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
152000 | Order Processing | Report | OR12 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
153000 | Order Processing | Report | OR13 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
154000 | Order Processing | Report | OR14 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
155000 | Order Processing | Report | OR15 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
156000 | Order Processing | Report | OR16 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
157000 | Order Processing | Smoke Test | OZ1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
158000 | Order Processing | Smoke Test | OZ2 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
159000 | Order Processing | Smoke Test | OZ3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
160000 | Order Processing | Smoke Test | OZ4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
161000 | Order Processing | Smoke Test | OZ5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
162000 | Order Processing | Smoke Test | OZ6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
163000 | Order Processing | Smoke Test | OZ7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
164000 | Order Processing | Smoke Test | OZ8 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
165000 | Order Processing | Smoke Test | OZ9 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
166000 | Order Processing | Smoke Test | OF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
167000 | Order Processing | Smoke Test | OF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
168000 | Order Processing | Smoke Test | OF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
169000 | Order Processing | Smoke Test | OF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
170000 | Order Processing | Smoke Test | OF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
171000 | Order Processing | Smoke Test | OF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
172000 | Order Processing | Smoke Test | OF7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
173000 | Order Processing | Smoke Test | OF8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
174000 | Order Processing | Smoke Test | OF9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
175000 | Raw Materials | Smoke Test | MU1 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
176000 | Raw Materials | Smoke Test | MU2 |  | Launch without error message and review basic functionality | 1 | Failed | Mark Tyndall | 2017-04-17 | Error Message (293)
177000 | Raw Materials | Smoke Test | MU3 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
178000 | Raw Materials | Smoke Test | MU4 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
179000 | Raw Materials | Smoke Test | MU5 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
180000 | Raw Materials | Smoke Test | MU6 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
181000 | Raw Materials | Smoke Test | MU7 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
182000 | Raw Materials | Smoke Test | MU8 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
183000 | Raw Materials | Smoke Test | MC1 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
184000 | Raw Materials | Smoke Test | MC2 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
185000 | Raw Materials | Smoke Test | MC3 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
186000 | Raw Materials | Smoke Test | MG |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
187000 | Raw Materials | Smoke Test | MQ1 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
188000 | Raw Materials | Smoke Test | MQ2 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
189000 | Raw Materials | Report | MR1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
190000 | Raw Materials | Report | MR2 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
191000 | Raw Materials | Report | MR3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
192000 | Raw Materials | Report | MR4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
193000 | Raw Materials | Report | MR5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
194000 | Raw Materials | Report | MR6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
195000 | Raw Materials | Report | MR7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
196000 | Raw Materials | Report | MR8 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
197000 | Raw Materials | Report | MR9 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
198000 | Raw Materials | Report | MR10 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
199000 | Raw Materials | Report | MR11 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
200000 | Raw Materials | Report | MR12 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
201000 | Raw Materials | Report | MR13 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
202000 | Raw Materials | Report | MR14 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
203000 | Raw Materials | Smoke Test | MF1 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
204000 | Raw Materials | Smoke Test | MF2 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
205000 | Raw Materials | Smoke Test | MF3 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
206000 | Raw Materials | Smoke Test | MF4 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
207000 | Raw Materials | Smoke Test | MF5 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
208000 | Raw Materials | Smoke Test | MF6 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
209000 | Finished Goods | Smoke Test | IU1 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
210000 | Finished Goods | Smoke Test | IU2 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
211000 | Finished Goods | Smoke Test | IU3 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
212000 | Finished Goods | Smoke Test | IU4 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
213000 | Finished Goods | Smoke Test | IU5 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
214000 | Finished Goods | Smoke Test | IU6 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
215000 | Finished Goods | Smoke Test | IU7 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
216000 | Finished Goods | Smoke Test | IU8 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
217000 | Finished Goods | Smoke Test | IU9 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
218000 | Finished Goods | Smoke Test | IC1 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
219000 | Finished Goods | Smoke Test | IC2 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
220000 | Finished Goods | Smoke Test | IC3 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
221000 | Finished Goods | Smoke Test | IW |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
222000 | Finished Goods | Smoke Test | IQ1 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
223000 | Finished Goods | Smoke Test | IQ2 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
224000 | Finished Goods | Smoke Test | IR1 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
225000 | Finished Goods | Smoke Test | IR2 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
226000 | Finished Goods | Smoke Test | IR3 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
227000 | Finished Goods | Smoke Test | IR4 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
228000 | Finished Goods | Smoke Test | IR5 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
229000 | Finished Goods | Smoke Test | IR6 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
230000 | Finished Goods | Smoke Test | IR7 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
231000 | Finished Goods | Smoke Test | IR8 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
232000 | Finished Goods | Smoke Test | IR9 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
233000 | Finished Goods | Smoke Test | IR10 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
234000 | Finished Goods | Smoke Test | IR11 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
235000 | Finished Goods | Smoke Test | IR12 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
236000 | Finished Goods | Smoke Test | IR13 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
237000 | Finished Goods | Smoke Test | IR14 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
238000 | Finished Goods | Smoke Test | IR15 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
239000 | Finished Goods | Report | IL1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
240000 | Finished Goods | Report | IL2 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
241000 | Finished Goods | Report | IL3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
242000 | Finished Goods | Report | IL4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
243000 | Finished Goods | Report | IL5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
244000 | Finished Goods | Report | IL6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
245000 | Finished Goods | Report | IL7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
246000 | Finished Goods | Report | IL8 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
247000 | Finished Goods | Report | IL9 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
248000 | Finished Goods | Report | IL10 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
249000 | Finished Goods | Report | IL11 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
250000 | Finished Goods | Report | IL12 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
251000 | Finished Goods | Report | IL13 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
252000 | Finished Goods | Report | IL14 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
253000 | Finished Goods | Report | IL15 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
254000 | Finished Goods | Smoke Test | IF1 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
255000 | Finished Goods | Smoke Test | IF2 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
256000 | Finished Goods | Smoke Test | IF3 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
257000 | Finished Goods | Smoke Test | IF4 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
258000 | Finished Goods | Smoke Test | IF5 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
259000 | Finished Goods | Smoke Test | IF6 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
260000 | Finished Goods | Smoke Test | IF7 |  | Launch without error message and review basic functionality | 1 | Passed | Mark Tyndall | 2017-04-17
261000 | Sales Reports | Smoke Test | HC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
262000 | Sales Reports | Smoke Test | HB |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
263000 | Sales Reports | Smoke Test | HF |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
264000 | Sales Reports | Smoke Test | HT |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
265000 | Sales Reports | Smoke Test | HW |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
266000 | Sales Reports | Smoke Test | HZ |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
267000 | Sales Reports | Smoke Test | HV |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
268000 | Sales Reports | Smoke Test | HY |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
269000 | Sales Reports | Smoke Test | HL |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
270000 | Sales Reports | Smoke Test | HS |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
271000 | Sales Reports | Smoke Test | HM1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
| Sales Reports | Smoke Test | HM2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
| Sales Reports | Smoke Test | HM3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
| Sales Reports | Smoke Test | HM4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
| Sales Reports | Smoke Test | HM5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
| Sales Reports | Smoke Test | HM6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
272000 | Sales Reports | Report | HR1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
273000 | Sales Reports | Report | HR2 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
274000 | Sales Reports | Report | HR3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
275000 | Sales Reports | Report | HR4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
276000 | Sales Reports | Report | HR5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
277000 | Sales Reports | Report | HR6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
278000 | Sales Reports | Report | HR7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
279000 | Sales Reports | Report | HR8 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
280000 | Sales Reports | Report | HR9 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
281000 | Sales Reports | Report | HR10 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
282000 | Sales Reports | Report | HR11 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
283000 | Sales Reports | Report | HR12 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
284000 | Sales Reports | Report | HR13 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
285000 | Sales Reports | Report | HR14 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
286000 | Sales Reports | Report | HR15 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
287000 | Sales Reports | Report | HR16 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-17
288000 | Data Collection | Smoke Test | DU |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
289000 | Data Collection | Smoke Test | DF |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
290000 | Data Collection | Smoke Test | DL1 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
291000 | Data Collection | Smoke Test | DL2 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
292000 | Data Collection | Smoke Test | DL3 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
293000 | Data Collection | Smoke Test | DW |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
294000 | Data Collection | Smoke Test | DT |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
295000 | Data Collection | Smoke Test | DQ1 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
296000 | Data Collection | Smoke Test | DR1 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
297000 | Data Collection | Smoke Test | DR2 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
298000 | Data Collection | Smoke Test | DR3 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
299000 | Data Collection | Smoke Test | DR4 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
300000 | Data Collection | Smoke Test | DR5 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
301000 | Data Collection | Smoke Test | DR6 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
302000 | Data Collection | Smoke Test | DR7 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
303000 | Data Collection | Smoke Test | DR8 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
304000 | Data Collection | Smoke Test | DR9 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
305000 | Data Collection | Smoke Test | DR10 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
306000 | Data Collection | Smoke Test | DR11 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
307000 | Data Collection | Smoke Test | DR12 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
308000 | Data Collection | Smoke Test | DR13 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
309000 | Data Collection | Smoke Test | DR14 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
310000 | Data Collection | Smoke Test | DR15 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
311000 | Data Collection | Smoke Test | DE1 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
|  |  | JU1 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
313000 | Jobs | Smoke Test | JU2 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
314000 | Jobs | Smoke Test | JU3 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
315000 | Jobs | Smoke Test | JU4 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
316000 | Jobs | Smoke Test | JU5 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
317000 | Jobs | Smoke Test | JU6 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
319000 | Jobs | Smoke Test | JU7 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
320000 | Jobs | Smoke Test | JU8 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
321000 | Jobs | Smoke Test | JC |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
322000 | Jobs | Smoke Test | JQ1 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
323000 | Jobs | Report | JR1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
324000 | Jobs | Report | JR2 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
325000 | Jobs | Report | JR3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
326000 | Jobs | Report | JR4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
327000 | Jobs | Report | JR5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
328000 | Jobs | Report | JR6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
329000 | Jobs | Report | JR7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
330000 | Jobs | Report | JR8 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
331000 | Jobs | Report | JR9 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
332000 | Jobs | Report | JR10 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
333000 | Jobs | Report | JR11 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
334000 | Jobs | Report | JR12 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
335000 | Jobs | Report | JR13 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
336000 | Jobs | Report | JR14 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
337000 | Jobs | Report | JR15 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
338000 | Jobs | Report | JL1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
339000 | Jobs | Report | JL2 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
340000 | Jobs | Report | JL3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
341000 | Jobs | Report | JL4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
342000 | Jobs | Report | JL5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
343000 | Jobs | Report | JL6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
344000 | Jobs | Report | JL7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
345000 | Jobs | Smoke Test | JF1 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
346000 | Jobs | Smoke Test | JF2 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
347000 | Jobs | Smoke Test | JF3 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
348000 | Jobs | Smoke Test | JF4 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
349000 | Jobs | Smoke Test | JF5 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
| Jobs | Smoke Test | JF6 |  | Launch without error message and review basic functionality | 1 | Passed | Ron Stark | 2017-04-17
350000 | Scheduler | Smoke Test | S3 |  | Launch without error message and review basic functionality | 1 | failed | Ron Stark | 2017-04-17 | Error messages on load
|  | Smoke Test | PU1 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Error messages on load
|  | Smoke Test | PU2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
351000 | Purchasing | Smoke Test | PU3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
352000 | Purchasing | Smoke Test | PU4 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Error messages on load
353000 | Purchasing | Smoke Test | PQ1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17 | Error messages on load
354000 | Purchasing | Report | PR1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
355000 | Purchasing | Report | PR2 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
356000 | Purchasing | Report | PR3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
357000 | Purchasing | Report | PR4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
358000 | Purchasing | Report | PR5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
359000 | Purchasing | Report | PR6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
360000 | Purchasing | Report | PR7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
361000 | Purchasing | Report | PR8 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
362000 | Purchasing | Report | PR9 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
363000 | Purchasing | Report | PR10 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
364000 | Purchasing | Report | PR11 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
365000 | Purchasing | Report | PR12 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
366000 | Purchasing | Report | PR13 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
367000 | Purchasing | Report | PR14 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
368000 | Purchasing | Smoke Test | PF1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
369000 | Purchasing | Smoke Test | PF2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
370000 | Receivables | Smoke Test | AU1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
371000 | Receivables | Smoke Test | AU2 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Error message substring
372000 | Receivables | Smoke Test | AU3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
373000 | Receivables | Smoke Test | AU4 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Error message substring
374000 | Receivables | Smoke Test | AU5 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
375000 | Receivables | Smoke Test | AW1 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Error Message
376000 | Receivables | Smoke Test | AW2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
377000 | Receivables | Smoke Test | AW3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
378000 | Receivables | Smoke Test | AW4 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Substring error
379000 | Receivables | Smoke Test | AC1 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Error message
380000 | Receivables | Smoke Test | AC2 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Error message
381000 | Receivables | Smoke Test | AC3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
382000 | Receivables | Smoke Test | AC4 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Substring error
383000 | Receivables | Smoke Test | AC5 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
384000 | Receivables | Smoke Test | AC6 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Substring error
385000 | Receivables | Smoke Test | AC7 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
386000 | Receivables | Smoke Test | AC8 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Substring error
387000 | Receivables | Smoke Test | AB |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
388000 | Receivables | Smoke Test | AQ1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
389000 | Receivables | Smoke Test | AQ2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
390000 | Receivables | Smoke Test | AQ2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
391000 | Receivables | Smoke Test | AQ3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
392000 | Receivables | Smoke Test | AQ4 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
393000 | Receivables | Smoke Test | AQ5 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
394000 | Receivables | Smoke Test | AR1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
395000 | Receivables | Smoke Test | AR2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
396000 | Receivables | Smoke Test | AR3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
397000 | Receivables | Smoke Test | AR4 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
398000 | Receivables | Smoke Test | AR5 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
399000 | Receivables | Smoke Test | AR6 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
400000 | Receivables | Smoke Test | AR7 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
401000 | Receivables | Smoke Test | AR8 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
402000 | Receivables | Smoke Test | AR9 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
403000 | Receivables | Smoke Test | AR10 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
404000 | Receivables | Smoke Test | AR11 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
405000 | Receivables | Smoke Test | AR12 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
406000 | Receivables | Smoke Test | AR13 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
407000 | Receivables | Smoke Test | AR14 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
408000 | Receivables | Smoke Test | AR15 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
409000 | Receivables | Smoke Test | AR16 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
410000 | Receivables | Smoke Test | AL1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
411000 | Receivables | Smoke Test | AL2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
412000 | Receivables | Smoke Test | AL3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
413000 | Receivables | Smoke Test | AF1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
414000 | Receivables | Smoke Test | AF2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
415000 | Receivables | Smoke Test | AF3 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | error message - budgets tab
416000 | Receivables | Smoke Test | AF4 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
417000 | Receivables | Smoke Test | AF5 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
418000 | Receivables | Smoke Test | AF6 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
419000 | Receivables | Smoke Test | AF7 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
420000 | Receivables | Smoke Test | AF8 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
421000 | Payables | Smoke Test | VU1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
422000 | Payables | Smoke Test | VU2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
423000 | Payables | Smoke Test | VU3 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Error substring
424000 | Payables | Smoke Test | AW1 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Error message
425000 | Payables | Smoke Test | AW2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
|  |  | AW3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
|  |  | AW4 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Substring error
426000 | Payables | Smoke Test | VB1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
427000 | Payables | Smoke Test | VB2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
428000 | Payables | Smoke Test | VB3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
429000 | Payables | Smoke Test | VC1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
430000 | Payables | Smoke Test | VC2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
431000 | Payables | Smoke Test | VC3 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Error substring
432000 | Payables | Smoke Test | VC4 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
433000 | Payables | Smoke Test | VC5 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Error substring
434000 | Payables | Smoke Test | VT1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
435000 | Payables | Smoke Test | VT2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
436000 | Payables | Smoke Test | VT3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
437000 | Payables | Smoke Test | VT4 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
438000 | Payables | Smoke Test | VL1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
439000 | Payables | Smoke Test | VL2 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Error substring
440000 | Payables | Smoke Test | VL3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
441000 | Payables | Smoke Test | VQ1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
442000 | Payables | Smoke Test | VQ2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
443000 | Payables | Smoke Test | VQ3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
444000 | Payables | Smoke Test | VQ4 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
445000 | Payables | Report | VR1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
446000 | Payables | Report | VR2 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
447000 | Payables | Report | VR3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
448000 | Payables | Report | VR4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
449000 | Payables | Report | VR5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
450000 | Payables | Report | VR6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
451000 | Payables | Report | VR7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
452000 | Payables | Report | VR8 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
453000 | Payables | Report | VR9 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
454000 | Payables | Report | VR10 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
455000 | Payables | Report | VR11 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
456000 | Payables | Report | VR12 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
457000 | Payables | Report | VR13 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
458000 | Payables | Report | VR14 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
459000 | Payables | Report | VR15 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
460000 | Payables | Smoke Test | VF1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
461000 | Payables | Smoke Test | VF2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
462000 | Payables | Smoke Test | VF3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
463000 | Payables | Smoke Test | VF4 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
464000 | Payables | Smoke Test | VF5 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
465000 | Payables | Smoke Test | VF6 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
| Payables | Smoke Test | VF7 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
466000 | General Ledger | Smoke Test | GU1 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Error Message
467000 | General Ledger | Smoke Test | GU2 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-17 | Error Message
468000 | General Ledger | Smoke Test | GU3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-17
469000 | General Ledger | Smoke Test | GU4 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18 | error Message
470000 | General Ledger | Smoke Test | GU5 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
471000 | General Ledger | Smoke Test | GC |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
472000 | General Ledger | Smoke Test | GY |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
473000 | General Ledger | Smoke Test | GT |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
474000 | General Ledger | Smoke Test | GW1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
475000 | General Ledger | Smoke Test | GW2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
476000 | General Ledger | Smoke Test | GW3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
477000 | General Ledger | Smoke Test | GQ |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-18 | Credit Status Tab - query br_table
478000 | General Ledger | Smoke Test | GR1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
479000 | General Ledger | Report | GR1 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
| General Ledger | Report | GR2 | OK = Passed Testing | Launch without error message and review basic functionality |  | Passed | Wade Kaldawi | 2017-04-18
480000 | General Ledger | Report | GR3 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
481000 | General Ledger | Report | GR4 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
482000 | General Ledger | Report | GR5 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
483000 | General Ledger | Report | GR6 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
484000 | General Ledger | Report | GR7 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
485000 | General Ledger | Report | GR8 | OK = Passed Testing | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
486000 | General Ledger | Report | GR9 |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-18 | Substring error
487000 | General Ledger | Smoke Test | GF1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
488000 | General Ledger | Smoke Test | GF2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
489000 | General Ledger | Smoke Test | GF3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
490000 | General Ledger | Smoke Test | GF4 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
491000 | General Ledger | Smoke Test | GF5 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
492000 | General Ledger | Smoke Test | GF6 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
493000 | System | Smoke Test | NL1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
494000 | System | Smoke Test | NL2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
495000 | System | Smoke Test | NF1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
496000 | System | Smoke Test | NF2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
497000 | System | Smoke Test | NF3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
498000 | System | Smoke Test | NF4 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
499000 | System | Smoke Test | NF5 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
500000 | System | Smoke Test | NF6 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
501000 | System | Smoke Test | NF7 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
502000 | System | Smoke Test | NF8 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
503000 | System | Smoke Test | NF9 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
504000 | System | Smoke Test | BF10 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
505000 | System | Smoke Test | NF11 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
506000 | System | Smoke Test | NF12 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
507000 | System | Smoke Test | NF13 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
508000 | System | Smoke Test | NF14 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
509000 | System | Smoke Test | NF15 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
510000 | System | Smoke Test | NY1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
511000 | System | Smoke Test | NY2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
512000 | System | Smoke Test | NY3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
513000 | System | Smoke Test | NY4 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
514000 | System | Smoke Test | NY5 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
515000 | System | Smoke Test | NY6 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
516000 | System | Smoke Test | NY7 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
517000 | System | Smoke Test | NY8 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
518000 | System | Smoke Test | NY9 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
519000 | System | Smoke Test | NY10 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
520000 | System | Smoke Test | NY11 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
521000 | System | Smoke Test | NY12 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
522000 | System | Smoke Test | NY13 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
523000 | System | Smoke Test | NY14 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
524000 | System | Smoke Test | NY15 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
525000 | System | Smoke Test | NU |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
526000 | System | Smoke Test | NC |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
527000 | System | Smoke Test | NB |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-18 | error - ./menu.lst was not found.
528000 | System | Smoke Test | NK1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
529000 | System | Smoke Test | NK2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
530000 | System | Smoke Test | NK3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
| System | Smoke Test | NK4 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
| System | Smoke Test | NK5 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
531000 | System | Smoke Test | NR |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
532000 | System | Smoke Test | NT |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
533000 | System | Smoke Test | NQ1 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
534000 | System | Smoke Test | NQ2 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
535000 | System | Smoke Test | NQ3 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
536000 | System | Smoke Test | NQ4 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
537000 | System | Smoke Test | NQ5 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
538000 | System | Smoke Test | NQ6 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
539000 | System | Smoke Test | NQ7 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
540000 | System | Smoke Test | NQ8 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
541000 | System | Smoke Test | NQ9 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
542000 | System | Smoke Test | NQ10 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
543000 | System | Smoke Test | NQ11 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
544000 | System | Smoke Test | NQ12 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
545000 | System | Smoke Test | NQ13 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
546000 | System | Smoke Test | NQ14 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
547000 | System | Smoke Test | NQ15 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
548000 | System | Smoke Test | NQ16 |  | Launch without error message and review basic functionality | 1 | Passed | Wade Kaldawi | 2017-04-18
549000 | System | Smoke Test | NW |  | Launch without error message and review basic functionality | 1 | failed | Wade Kaldawi | 2017-04-18 | Error - "system" was not found (293)
550000 | System | Smoke Test | NZ1 |  | Launch without error message and review basic functionality | 2 | Passed | Wade Kaldawi | 2017-04-18
551000 | System | Smoke Test | NZ2 |  | Launch without error message and review basic functionality | 2 | Passed | Wade Kaldawi | 2017-04-18
552000 | System | Smoke Test | NZ3 |  | Launch without error message and review basic functionality | 2 | Passed | Wade Kaldawi | 2017-04-18
553000 | System | Smoke Test | NZ4 |  | Launch without error message and review basic functionality | 2 | Passed | Wade Kaldawi | 2017-04-18
554000 | System | Smoke Test | NZ5 |  | Launch without error message and review basic functionality | 2 | Passed | Wade Kaldawi | 2017-04-18
555000 | System | Smoke Test | NZ6 |  | Launch without error message and review basic functionality | 2 | Passed | Wade Kaldawi | 2017-04-18
556000 | System | Smoke Test | NZ7 |  | Launch without error message and review basic functionality | 2 | Passed | Wade Kaldawi | 2017-04-18
557000 | System | Smoke Test | NZ8 |  | Launch without error message and review basic functionality | 2 | Passed | Wade Kaldawi | 2017-04-18
558000 | System | Smoke Test | NZ9 |  | Launch without error message and review basic functionality | 2 | Passed | Wade Kaldawi | 2017-04-18
559000 | System | Smoke Test | NZ10 |  | Launch without error message and review basic functionality | 2 | Passed | Wade Kaldawi | 2017-04-18
| System | Smoke Test | NZ11 |  | Launch without error message and review basic functionality | 2 | Passed | Wade Kaldawi | 2017-04-18
| System | Smoke Test | NZ12 |  | Launch without error message and review basic functionality | 2 | Passed | Wade Kaldawi | 2017-04-18
560000 | System | Smoke Test | NR1 |  | Launch without error message and review basic functionality | 2 | Passed | Wade Kaldawi | 2017-04-18
561000 | System | Smoke Test | NR2 |  | Launch without error message and review basic functionality | 99 | failed | Wade Kaldawi | 2017-04-18 | Procedure asi/sr Does not exist
562000 | System | Smoke Test | NR3 |  | Launch without error message and review basic functionality | 2 | Passed | Wade Kaldawi | 2017-04-18
563000 | System | Smoke Test | NR4 |  | Launch without error message and review basic functionality | 2 | Passed | Wade Kaldawi | 2017-04-18
564000 | System | Smoke Test | NR5 |  | Launch without error message and review basic functionality | 2 | Passed | Wade Kaldawi | 2017-04-18
565000 | System | Smoke Test | Exit |  | Launch without error message and review basic functionality | 2 | Passed | Wade Kaldawi | 2017-04-18

## Advantzware Add-ons
[6 empty] | Run | 98.81%
| Addons - Testing |  |  |  |  | Passed | 97.59%
[6 empty] | Failed | 2.41%
| Tests in this color have Scripts on another sheet ( use "Note" format at top) |  |  |  |  | Blocked | 0%
Test # | Category | Sub-category | Application | Time Speed | Test | Priority | Passed | Tester Name | Test Date | Failure Notes | Failure Task | Notes
101000 | Touch Screen Menu | Smoke Test | TD |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2017-04-20
102000 | Touch Screen Posting | Smoke Test | TP |  | Post Touch Data to ASI Database | 1 | Passed | John Loeb | 2017-04-20
102100 | Report | Smoke Test | TR1 |  | Daily Summary | 1 | Passed | John Loeb | 2017-04-20
102200 | Report | Smoke Test | TR2 |  | Employees List | 1 | Passed | John Loeb | 2017-04-20
102300 | Report | Smoke Test | TR3 |  | Machine Transactions | 1 | Passed | John Loeb | 2017-04-20
103000 | Report | Smoke Test | TR4 |  | Completed Machine Jobs List | 1 | Passed | John Loeb | 2017-04-20
103100 | Report | Smoke Test | TR5 |  | Shifts List | 1 | Passed | John Loeb | 2017-04-20
103200 | Report | Smoke Test | TR6 |  | Machine Assigned Chrg Cds List | 1 | Passed | John Loeb | 2017-04-20
103300 | Report | Smoke Test | TR7 |  | Machine Assigned Shifts List | 1 | Passed | John Loeb | 2017-04-20
103400 | Report | Smoke Test | TR8 |  | Employee Types List | 1 | Passed | John Loeb | 2017-04-20
| Report | Smoke Test | TR9 |  | Labor Report | 1 | Passed | John Loeb | 2017-04-20
| Report | Smoke Test | TR10 |  | Employee Time by Job | 1 | Passed | John Loeb | 2017-04-20
| Report | Smoke Test | TR11 |  | In\Out Transaction Report | 1 | Failed | John Loeb | 2017-04-20 | Error Message
| Report | Smoke Test | TR12 |  | Employee Time Sheet | 1 | Passed | John Loeb | 2017-04-20
| Report | Smoke Test | TR13 |  | Unreported Labor Report | 1 | Passed | John Loeb | 2017-04-20
| Report | Smoke Test | TR14 |  | Machine Notes Report | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | TF1 |  | Employees | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | TF2 |  | Employee Transaction Summary | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | TF3 |  | Machine Transactions | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | TF4 |  | Employee Transactions | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | TF5 |  | Completed Machine Jobs | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | TF6 |  | Job Sequence | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | TF7 |  | Shifts List | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | TF8 |  | Machine Assigned Charge Codes | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | TF9 |  | Machine Assigned Shifts List | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | TF10 |  | Employee Default Rates | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | TF11 |  | Employee Types | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | TF12 |  | RePost Touch Data to ASI Database | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | TF13 |  | Purge Employee Transaction | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | TF14 |  | Purge Touch Data | 1 | Passed | John Loeb | 2017-04-20
| Employee Tracking | Smoke Test | TF15 |  | Purge Zero Time Transaction | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | TF1 |  | Purge Zero Time Transaction | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | SM1 |  | Receive Materials | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | SM2 |  | Issue Materials | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | SM3 |  | Job Returns | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | SM4 |  | Transfer Materials | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | SM5 |  | Move Materials | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | SM6 |  | Count Materials | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | SM7 |  | Delete Materials | 1 | Passed | John Loeb | 2017-04-20
| Material Menu | Smoke Test | SM8 |  | Post Materials | 1 | Failed | John Loeb | 2017-04-20
| Material Menu | Smoke Test | SM9 |  | Scan Vendor Tag | 1 | Passed | John Loeb | 2016-04-20
| Material Menu | Smoke Test | SF1 |  | Receive Goods | 1 | Passed | John Loeb | 2017-04-20
| Material Menu | Smoke Test | SF2 |  | Move Receipts | 1 | Passed | John Loeb | 2017-04-20
| Material Menu | Smoke Test | SF3 |  | Transfer Goods | 1 | Passed | John Loeb | 2017-04-20
| Material Menu | Smoke Test | SF4 |  | Count Goods | 1 | Passed | John Loeb | 2017-04-20
| Material Menu | Smoke Test | SF5 |  | Delete Goods | 1 | Passed | John Loeb | 2017-04-20
| Material Menu | Smoke Test | SF6 |  | Return Goods | 1 | Passed | John Loeb | 2017-04-20
| Material Menu | Smoke Test | SF7 |  | Post Goods | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | SF8 |  | Consolidate Tags | 1 | Passed | John Loeb | 2017-04-20
| FG Warehouse | Smoke Test | SF9 |  | Close | 1 | Passed | John Loeb | 2017-04-20
| FG Warehouse | Smoke Test | SB1 |  | Create BOL | 1 | Passed | John Loeb | 2017-04-20
| FG Warehouse | Smoke Test | SB2 |  | Update Release | 1 | Passed | John Loeb | 2017-04-20
| FG Warehouse | Smoke Test | SB3 |  | Print Pick Ticket | 1 | Passed | John Loeb | 2017-04-20
| FG Warehouse | Smoke Test | SB4 |  | Close | 1 | Passed | John Loeb | 2017-04-20
| FG Warehouse | Smoke Test | SL1 |  | Make FG Load Tags | 1 | Passed | John Loeb | 2017-04-20
| FG Warehouse | Smoke Test | SL2 |  | Make Raw Mat'l Tags | 1 | Passed | John Loeb | 2017-04-20
| FG Warehouse | Smoke Test | SL3 |  | Scan Case Label | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | SL4 |  | Make WIP Tags | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | SL5 |  | File Maintenance | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | SR1 |  | Production report | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | MP |  | Prospects and Customer Names | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | ML |  | List Management | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | MR1 |  | Contact List | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | MR2 |  | Mail List Merge | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | MR3 |  | Mail List Label | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | MF1 |  | Copy Customers to Contact Mgr. | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | MF2 |  | Download to Laptop |  | Passed | John Loeb | 2017-04-20
|  | Smoke Test | MF3 |  | Upload to Server | 1 | Passed | John Loeb | 2017-04-20
104000 |  | Smoke Test | QR |  | Request For Quotes | 1 | Passed | John Loeb | 2017-04-20
104100 |  | Smoke Test | QL1 |  | Single RFQ List | 1 | Passed | John Loeb | 2017-04-20
104200 |  | Smoke Test | QL2 |  | RFQ List | 1 | Passed | John Loeb | 2017-04-20
104300 |  | Smoke Test | QF1 |  | RFQ Maintenance | 1 | Passed | John Loeb | 2017-04-20
105000 |  | Smoke Test | WD1 |  | Item Receipt | 1 | Passed | John Loeb | 2017-04-20
106000 |  | Smoke Test | WD2 |  | Item Usage | 1 | Passed | John Loeb | 2017-04-20
107000 |  | Smoke Test | WR1 |  | Customer Inventory Report 1 | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | WR2 |  | Customer Inventory Report 2 | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | WR3 |  | Red Flag Report | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | WR4 |  | Exceptions Report | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | WF1 |  | Item File Maintenance | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | WF2 |  | Plant File Maintenance | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | WF3 |  | Vendor Cross Reference | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | WF4 |  | Warehouse History | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | WF5 |  | Customer Inventory | 1 | Passed | John Loeb | 2017-04-20
|  | Smoke Test | EI |  | No Dev | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
108000 |  | Smoke Test |  |  |  | 1 |  | John Loeb
109000 |  | Smoke Test |  |  |  | 1 |  | John Loeb
110000 |  | Smoke Test |  |  |  | 1 |  | John Loeb
111000 |  | Smoke Test |  |  |  | 1 |  | John Loeb
112000 |  | Smoke Test |  |  |  | 1 |  | John Loeb
113000 |  | Smoke Test |  |  |  | 1 |  | John Loeb
114000 |  | Smoke Test |  |  |  | 1 |  | John Loeb
115000 |  | Smoke Test |  |  |  | 1 |  | John Loeb
116000 |  | Smoke Test |  |  |  | 1 |  | John Loeb
117000 |  | Smoke Test |  |  |  | 1 |  | John Loeb
118000 |  | Smoke Test |  |  |  | 1 |  | John Loeb
119000 |  | Smoke Test |  |  |  | 1 |  | John Loeb
120000 |  | Smoke Test |  |  |  | 1 |  | John Loeb
121000 |  | Smoke Test |  |  |  | 1 |  | John Loeb
122000 |  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
|  | Smoke Test |  |  |  | 1 |  | John Loeb
123000
124000
125000
126000
127000
128000
129000
130000
131000
132000
133000
134000
135000
136000
137000
138000
139000
140000
141000
142000
143000
144000
145000
146000
147000
148000
149000
150000
151000
152000
153000
154000
155000
156000
157000
158000
159000
160000
161000
162000
163000
164000
165000
166000
167000
168000
169000
170000
171000
172000
173000
174000
175000
176000
177000
178000
179000
180000
181000
182000
183000
184000
185000
186000
187000
188000
189000
190000
191000
192000
193000
194000
195000
196000
197000
198000
199000
200000
201000
202000
203000
204000
205000
206000
207000
208000
209000
210000
211000
212000
213000
214000
215000
216000
217000
218000
219000
220000
221000
222000
223000
224000
225000
226000
227000
228000
229000
230000
231000
232000
233000
234000
235000
236000
237000
238000
239000
240000
241000
242000
243000
244000
245000
246000
247000
248000
249000
250000
251000
252000
253000
254000
255000
256000
257000
258000
259000
260000 | [11 empty] | Tabs Info not right
261000
262000
263000
264000
265000
266000
267000
268000
269000
270000
271000
272000
273000
274000
275000
276000
277000
278000
279000
280000
281000
282000
283000
284000
285000
286000
287000
288000
289000
290000
291000
292000
293000
294000
295000
296000
297000
298000
299000
300000
301000
302000
303000
304000
305000
306000
307000
308000
309000
310000
311000
312000
313000
314000
315000
316000
317000
319000
320000
321000
322000
323000
324000
325000
326000
327000
328000
329000
330000
331000
332000
333000
334000
335000
336000
337000
338000
339000
340000
341000
342000
343000
344000
345000
346000
347000
348000
349000
350000
351000
352000
353000
354000
355000
356000
357000
358000
359000
360000
361000
362000
363000
364000
365000
366000
367000
368000
369000
370000
371000
372000
373000
374000
375000
376000
377000
378000
379000
380000
381000
382000
383000
384000
385000
386000
387000
388000
389000
390000
391000
392000
393000
394000
395000
396000
397000
398000
399000
400000
401000
402000
403000
404000
405000
406000
407000
408000
409000
410000
411000
412000
413000
414000
415000
416000
417000
418000
419000
420000
421000
422000
423000
424000
425000
426000
427000
428000
429000
430000
431000
432000
433000
434000
435000
436000
437000
438000
439000
440000
441000
442000
443000
444000
445000
446000
447000
448000
449000
450000
451000
452000
453000
454000
455000
456000
457000
458000
459000
460000
461000
462000
463000
464000
465000
466000
467000
468000
469000
470000
471000
472000
473000
474000
475000
476000
477000
478000
479000
480000
481000
482000
483000
484000
485000
486000
487000
488000
489000
490000
491000
492000
493000
494000
495000
496000
497000
498000
499000
500000
501000
502000
503000
504000
505000
506000
507000
508000
509000
510000
511000
512000
513000
514000
515000
516000
517000
518000
519000
520000
521000
522000
523000
524000
525000
526000
527000
528000
529000
530000
531000
532000
533000
534000
535000
536000
537000
538000
539000
540000
541000
542000
543000
544000
545000
546000
547000
548000
549000
550000
551000
552000
553000
554000
555000
556000
557000
558000
559000
560000
561000
562000
563000
564000
565000

## Test Scripts - Estimating
v Use this filter to find the test
Script ID | Test # | Step # | Action | Expected Result | Actual Result (blank if Expected Result met) | Passed?
102100-01 | 102100 | 1
102100-02 | 102100 | 2
102100-03 | 102100 | 3
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00

## Test Scripts - Order Processing
v Use this filter to find the test
Script ID | Test # | Step # | Action | Expected Result | Actual Result (blank if Expected Result met) | Passed?
102100-01 | 102100 | 1
102100-02 | 102100 | 2
102100-03 | 102100 | 3
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00

## Test Data
Data Type | Data ID | Data Description
Estimate |  | Existing Single Item Estimate - Corrugated
Estimate |  | Existing Set Estimate - Corrugated
Order
BOL
OE Invoice
AR Invoice
Release
Job