## Test Master
[6 empty] | Run | 98.06%
[6 empty] | Passed | 99.6%
[6 empty] | Failed | 0.396%
| Tests in this color have Scripts on another sheet ( use "Note" format at top) |  |  |  |  | Blocked | 0%
Test # | Category | Sub-category | Application | Time Speed | Test | Priority | Passed | Tester Name | Test Date | Failure Notes | Failure Task | Notes
101000 | Estimating | Smoke Test | EF |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
102000 | Estimating | Smoke Test | EF |  | Choose a record on first browser. Click through all tabs. Validate that there are no error messages. | 2 | Passed | John Loeb | 2016-08-17
102100 | Estimating | Add Estimate | EF |  | Add an estimate for a single item | 3 |  | John Loeb
102200 | Estimating | Add Estimate | EF |  | Add an estimate for a tandem | 3
102300 | Estimating | Add Estimate | EF |  | Add an estimate for a set | 3
103000 | Estimating | Smoke Test | EC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
103100 | Estimating | Smoke Test | EC |  | Choose a record on first browser. Click through all tabs. Validate that there are no error messages. | 2 | Passed | John Loeb | 2016-08-17
103200 | Estimating | Add Estimate | EC |  | Add an estimate for a single item | 3 |  | John Loeb
103300 | Estimating | Add Estimate | EC |  | Add an estimate for a tandem | 3 |  | John Loeb
103400 | Estimating | Add Estimate | EC |  | Add an estimate for a set | 3 |  | John Loeb
|  |  | EQ |  | Quotes |  | Passed | John Loeb | 2016-08-17
|  |  | KY |  | Kopy Estime |  | Passed | John Loeb | 2016-08-17
|  |  | ES |  | Search for Estimates |  | Passed | John Loeb | 2016-08-17
|  |  | EG |  | Global Quote Price Change |  | Passed | John Loeb | 2016-08-17
|  |  | ET |  | Tools for Sales |  | Passed | John Loeb | 2016-08-17
|  | Report | ER1 | Passed | Control File |  | Passed | John Loeb | 2016-08-17
|  | Report | ER2 | Passed | machine File |  | Passed | John Loeb | 2016-08-17
|  | Report | ER3 | Passed | Style File |  | Passed | John Loeb | 2016-08-17
|  | Report | ER4 | Passed | Prep File |  | Passed | John Loeb | 2016-08-17
|  | Report | ER5 | Passed | Estimates List |  | Passed | John Loeb | 2016-08-17
|  | Report | ER6 | Passed | Quotes List |  | Passed | John Loeb | 2016-08-17
|  | Report | ER7 | Passed | prep List by Mat'l Type |  | Passed | John Loeb | 2016-08-17
|  | Report | ER8 | Passed | Estimate by Size |  | Passed | John Loeb | 2016-08-17
|  | Report | ER9 | Passed | Quoted price List |  | Passed | John Loeb | 2016-08-17
|  | Report | ER10 | Passed | Estimates List w/margins |  | Passed | John Loeb | 2016-08-17
|  |  | EB1 |  | Machine File |  | Passed | John Loeb | 2016-08-17
|  |  | EB2 |  | Folding Styles |  | Passed | John Loeb | 2016-08-17
|  |  | EB3 |  | Corrugated Styles |  | Passed | John Loeb | 2016-08-17
|  |  | EB4 |  | Box Design |  | Passed | John Loeb | 2016-08-17
|  |  | EB5 |  | Stacking Patterns |  | Passed | John Loeb | 2016-08-17
|  |  | EB6 |  | Stacking matrix |  | Passed | John Loeb | 2016-08-17
|  |  | EB7 |  | Flute Unit Counts |  | Passed | John Loeb | 2016-08-17
|  |  | EB8 |  | Prep and Die File |  | Passed | John Loeb | 2016-08-17
|  |  | EB9 |  | Cost Estimate Control |  | Passed | John Loeb | 2016-08-17
|  |  | EB10 |  | Truck / Common Carriers |  | Passed | John Loeb | 2016-08-17
|  |  | EB11 |  | Machine Routings |  | Passed | John Loeb | 2016-08-17
|  |  | EB12 |  | Score Types |  | Passed | John Loeb | 2016-08-17
|  |  | EB13 |  | machine Attachments / Adders |  | Passed | John Loeb | 2016-08-17
104000 | Order Processing | Smoke Test | OU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
104100 | Order Processing | Smoke Test | OU1 |  | Choose a record on first browser. Click through all tabs. Validate that there are no error messages. | 2 | Passed | John Loeb | 2016-08-17
104200 | Order Processing | Add Order | OU1 |  | Add an order for a single item estimate. Validate that the order gets created with the correct information. | 3 |  | John Loeb | 2016-08-17
104300 | Order Processing | Add Order | OU1 |  | Add an order for 3 items. Validate that the order gets created with all three items with the correct information. | 3 |  | John Loeb | 2016-08-17
105000 | Order Processing | Smoke Test | OU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
106000 | Order Processing | Smoke Test | OU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
107000 | Order Processing | Smoke Test | OU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
108000 | Order Processing | Smoke Test | OU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
109000 | Order Processing | Smoke Test | OU6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
110000 | Order Processing | Smoke Test | OU7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
111000 | Order Processing | Smoke Test | OU8 |  | Launch without error message and review basic functionality | 99 |  | John Loeb | \
112000 | Order Processing | Smoke Test | OU9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
113000 | Order Processing | Smoke Test | OU10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
114000 | Order Processing | Smoke Test | OU11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
115000 | Order Processing | Smoke Test | OT1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
116000 | Order Processing | Smoke Test | OT2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
117000 | Order Processing | Smoke Test | OT3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
118000 | Order Processing | Smoke Test | OT4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
119000 | Order Processing | Smoke Test | OT5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
120000 | Order Processing | Smoke Test | OS1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
121000 | Order Processing | Smoke Test | OS2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
122000 | Order Processing | Smoke Test | OS3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
123000 | Order Processing | Smoke Test | OS4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
124000 | Order Processing | Smoke Test | OS5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
125000 | Order Processing | Smoke Test | OS6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
126000 | Order Processing | Smoke Test | OS7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
127000 | Order Processing | Smoke Test | OS8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
128000 | Order Processing | Smoke Test | OB1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
129000 | Order Processing | Smoke Test | OB2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
130000 | Order Processing | Smoke Test | OB3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
131000 | Order Processing | Smoke Test | OB4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
132000 | Order Processing | Smoke Test | OB5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
133000 | Order Processing | Smoke Test | OL1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
134000 | Order Processing | Smoke Test | OL2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
135000 | Order Processing | Smoke Test | OL3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
136000 | Order Processing | Smoke Test | OC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
137000 | Order Processing | Smoke Test | OW |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
138000 | Order Processing | Smoke Test | OQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
139000 | Order Processing | Smoke Test | OQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
140000 | Order Processing | Smoke Test | OQ3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
141000 | Order Processing | Report | OR1 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
142000 | Order Processing | Report | OR2 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
143000 | Order Processing | Report | OR3 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
144000 | Order Processing | Report | OR4 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
145000 | Order Processing | Report | OR5 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
146000 | Order Processing | Report | OR6 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
147000 | Order Processing | Report | OR7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
148000 | Order Processing | Report | OR8 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
149000 | Order Processing | Report | OR9 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
150000 | Order Processing | Report | OR10 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
151000 | Order Processing | Report | OR11 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
152000 | Order Processing | Report | OR12 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
153000 | Order Processing | Report | OR13 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
154000 | Order Processing | Report | OR14 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
155000 | Order Processing | Report | OR15 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
156000 | Order Processing | Report | OR16 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
157000 | Order Processing | Smoke Test | OZ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
158000 | Order Processing | Smoke Test | OZ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
159000 | Order Processing | Smoke Test | OZ3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
160000 | Order Processing | Smoke Test | OZ4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
161000 | Order Processing | Smoke Test | OZ5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
162000 | Order Processing | Smoke Test | OZ6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
163000 | Order Processing | Smoke Test | OZ7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
164000 | Order Processing | Smoke Test | OZ8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
165000 | Order Processing | Smoke Test | OZ9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
166000 | Order Processing | Smoke Test | OF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
167000 | Order Processing | Smoke Test | OF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
168000 | Order Processing | Smoke Test | OF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
169000 | Order Processing | Smoke Test | OF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
170000 | Order Processing | Smoke Test | OF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
171000 | Order Processing | Smoke Test | OF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
172000 | Order Processing | Smoke Test | OF7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
173000 | Order Processing | Smoke Test | OF8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
174000 | Order Processing | Smoke Test | OF9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
175000 | Raw Materials | Smoke Test | MU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
176000 | Raw Materials | Smoke Test | MU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
177000 | Raw Materials | Smoke Test | MU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
178000 | Raw Materials | Smoke Test | MU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
179000 | Raw Materials | Smoke Test | MU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
180000 | Raw Materials | Smoke Test | MU6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
181000 | Raw Materials | Smoke Test | MU7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
182000 | Raw Materials | Smoke Test | MU8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
183000 | Raw Materials | Smoke Test | MC1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
184000 | Raw Materials | Smoke Test | MC2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
185000 | Raw Materials | Smoke Test | MC3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
186000 | Raw Materials | Smoke Test | MG |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
187000 | Raw Materials | Smoke Test | MQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
188000 | Raw Materials | Smoke Test | MQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
189000 | Raw Materials | Report | MR1 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
190000 | Raw Materials | Report | MR2 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
191000 | Raw Materials | Report | MR3 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
192000 | Raw Materials | Report | MR4 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
193000 | Raw Materials | Report | MR5 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
194000 | Raw Materials | Report | MR6 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
195000 | Raw Materials | Report | MR7 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
196000 | Raw Materials | Report | MR8 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
197000 | Raw Materials | Report | MR9 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
198000 | Raw Materials | Report | MR10 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
199000 | Raw Materials | Report | MR11 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
200000 | Raw Materials | Report | MR12 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
201000 | Raw Materials | Report | MR13 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
202000 | Raw Materials | Report | MR14 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
203000 | Raw Materials | Smoke Test | MF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
204000 | Raw Materials | Smoke Test | MF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
205000 | Raw Materials | Smoke Test | MF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
206000 | Raw Materials | Smoke Test | MF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
207000 | Raw Materials | Smoke Test | MF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
208000 | Raw Materials | Smoke Test | MF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
209000 | Finished Goods | Smoke Test | IU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
210000 | Finished Goods | Smoke Test | IU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
211000 | Finished Goods | Smoke Test | IU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
212000 | Finished Goods | Smoke Test | IU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
213000 | Finished Goods | Smoke Test | IU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
214000 | Finished Goods | Smoke Test | IU6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
215000 | Finished Goods | Smoke Test | IU7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
216000 | Finished Goods | Smoke Test | IU8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
217000 | Finished Goods | Smoke Test | IU9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
218000 | Finished Goods | Smoke Test | IC1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
219000 | Finished Goods | Smoke Test | IC2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
220000 | Finished Goods | Smoke Test | IC3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
221000 | Finished Goods | Smoke Test | IW |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
222000 | Finished Goods | Smoke Test | IQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
223000 | Finished Goods | Smoke Test | IQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
224000 | Finished Goods | Smoke Test | IR1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
225000 | Finished Goods | Smoke Test | IR2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
226000 | Finished Goods | Smoke Test | IR3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
227000 | Finished Goods | Smoke Test | IR4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
228000 | Finished Goods | Smoke Test | IR5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
229000 | Finished Goods | Smoke Test | IR6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
230000 | Finished Goods | Smoke Test | IR7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
231000 | Finished Goods | Smoke Test | IR8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
232000 | Finished Goods | Smoke Test | IR9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
233000 | Finished Goods | Smoke Test | IR10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
234000 | Finished Goods | Smoke Test | IR11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
235000 | Finished Goods | Smoke Test | IR12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
236000 | Finished Goods | Smoke Test | IR13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
237000 | Finished Goods | Smoke Test | IR14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
238000 | Finished Goods | Smoke Test | IR15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
239000 | Finished Goods | Report | IL1 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
240000 | Finished Goods | Report | IL2 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
241000 | Finished Goods | Report | IL3 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
242000 | Finished Goods | Report | IL4 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
243000 | Finished Goods | Report | IL5 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
244000 | Finished Goods | Report | IL6 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
245000 | Finished Goods | Report | IL7 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
246000 | Finished Goods | Report | IL8 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
247000 | Finished Goods | Report | IL9 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
248000 | Finished Goods | Report | IL10 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
249000 | Finished Goods | Report | IL11 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
250000 | Finished Goods | Report | IL12 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
251000 | Finished Goods | Report | IL13 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
252000 | Finished Goods | Report | IL14 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
253000 | Finished Goods | Report | IL15 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
254000 | Finished Goods | Smoke Test | IF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
255000 | Finished Goods | Smoke Test | IF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
256000 | Finished Goods | Smoke Test | IF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
257000 | Finished Goods | Smoke Test | IF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
258000 | Finished Goods | Smoke Test | IF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
259000 | Finished Goods | Smoke Test | IF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
260000 | Finished Goods | Smoke Test | IF7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17 |  |  | Tabs Info not right
261000 | Sales Reports | Smoke Test | HC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
262000 | Sales Reports | Smoke Test | HB |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
263000 | Sales Reports | Smoke Test | HF |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
264000 | Sales Reports | Smoke Test | HT |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
265000 | Sales Reports | Smoke Test | HW |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
266000 | Sales Reports | Smoke Test | HZ |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
267000 | Sales Reports | Smoke Test | HV |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
268000 | Sales Reports | Smoke Test | HY |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
269000 | Sales Reports | Smoke Test | HL |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
270000 | Sales Reports | Smoke Test | HS |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
271000 | Sales Reports | Smoke Test | HM1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
| Sales Reports | Smoke Test | HM2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
| Sales Reports | Smoke Test | HM3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
| Sales Reports | Smoke Test | HM4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
| Sales Reports | Smoke Test | HM5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
| Sales Reports | Smoke Test | HM6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
272000 | Sales Reports | Report | HR1 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
273000 | Sales Reports | Report | HR2 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
274000 | Sales Reports | Report | HR3 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
275000 | Sales Reports | Report | HR4 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
276000 | Sales Reports | Report | HR5 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
277000 | Sales Reports | Report | HR6 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
278000 | Sales Reports | Report | HR7 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
279000 | Sales Reports | Report | HR8 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
280000 | Sales Reports | Report | HR9 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
281000 | Sales Reports | Report | HR10 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
282000 | Sales Reports | Report | HR11 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
283000 | Sales Reports | Report | HR12 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
284000 | Sales Reports | Report | HR13 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
285000 | Sales Reports | Report | HR14 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
286000 | Sales Reports | Report | HR15 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
287000 | Sales Reports | Report | HR16 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
288000 | Data Collection | Smoke Test | DU |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
289000 | Data Collection | Smoke Test | DF |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
290000 | Data Collection | Smoke Test | DL1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
291000 | Data Collection | Smoke Test | DL2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
292000 | Data Collection | Smoke Test | DL3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
293000 | Data Collection | Smoke Test | DW |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
294000 | Data Collection | Smoke Test | DT |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
295000 | Data Collection | Smoke Test | DQ1 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-08-17 | Button error message
296000 | Data Collection | Smoke Test | DR1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
297000 | Data Collection | Smoke Test | DR2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
298000 | Data Collection | Smoke Test | DR3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
299000 | Data Collection | Smoke Test | DR4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
300000 | Data Collection | Smoke Test | DR5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
301000 | Data Collection | Smoke Test | DR6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
302000 | Data Collection | Smoke Test | DR7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
303000 | Data Collection | Smoke Test | DR8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
304000 | Data Collection | Smoke Test | DR9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
305000 | Data Collection | Smoke Test | DR10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
306000 | Data Collection | Smoke Test | DR11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
307000 | Data Collection | Smoke Test | DR12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
308000 | Data Collection | Smoke Test | DR13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
309000 | Data Collection | Smoke Test | DR14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
310000 | Data Collection | Smoke Test | DR15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
311000 | Data Collection | Smoke Test | DE1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
312000 | Jobs | Smoke Test | JU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
313000 | Jobs | Smoke Test | JU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
314000 | Jobs | Smoke Test | JU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
315000 | Jobs | Smoke Test | JU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
316000 | Jobs | Smoke Test | JU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
317000 | Jobs | Smoke Test | JU6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
319000 | Jobs | Smoke Test | JU7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
320000 | Jobs | Smoke Test | JU8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
321000 | Jobs | Smoke Test | JC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
322000 | Jobs | Smoke Test | JQ1 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-08-17 | error message
323000 | Jobs | Smoke Test | JR1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
324000 | Jobs | Smoke Test | JR2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
325000 | Jobs | Smoke Test | JR3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
326000 | Jobs | Smoke Test | JR4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
327000 | Jobs | Smoke Test | JR5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
328000 | Jobs | Smoke Test | JR6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
329000 | Jobs | Smoke Test | JR7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
330000 | Jobs | Smoke Test | JR8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
331000 | Jobs | Smoke Test | JR9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
332000 | Jobs | Smoke Test | JR10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
333000 | Jobs | Smoke Test | JR11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
334000 | Jobs | Smoke Test | JR12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
335000 | Jobs | Smoke Test | JR13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
336000 | Jobs | Smoke Test | JR14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
337000 | Jobs | Smoke Test | JR15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
338000 | Jobs | Report | JL1 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
339000 | Jobs | Report | JL2 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
340000 | Jobs | Report | JL3 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
341000 | Jobs | Report | JL4 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
342000 | Jobs | Report | JL5 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
343000 | Jobs | Report | JL6 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
344000 | Jobs | Report | JL7 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
345000 | Jobs | Smoke Test | JF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
346000 | Jobs | Smoke Test | JF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
347000 | Jobs | Smoke Test | JF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
348000 | Jobs | Smoke Test | JF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
349000 | Jobs | Smoke Test | JF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
| Jobs | Smoke Test | JF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
350000 | Scheduler | Smoke Test | S3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
|  | Smoke Test | PU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
|  | Smoke Test | PU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
351000 | Purchasing | Smoke Test | PU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
352000 | Purchasing | Smoke Test | PU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
353000 | Purchasing | Smoke Test | PQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
354000 | Purchasing | Report | PR1 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
355000 | Purchasing | Report | PR2 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
356000 | Purchasing | Report | PR3 | Passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
357000 | Purchasing | Report | PR4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
358000 | Purchasing | Report | PR5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
359000 | Purchasing | Report | PR6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
360000 | Purchasing | Report | PR7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
361000 | Purchasing | Report | PR8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
362000 | Purchasing | Report | PR9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
363000 | Purchasing | Report | PR10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
364000 | Purchasing | Report | PR11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
365000 | Purchasing | Report | PR12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
366000 | Purchasing | Report | PR13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
367000 | Purchasing | Report | PR14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
368000 | Purchasing | Smoke Test | PF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
369000 | Purchasing | Smoke Test | PF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
370000 | Receivables | Smoke Test | AU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
371000 | Receivables | Smoke Test | AU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
372000 | Receivables | Smoke Test | AU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
373000 | Receivables | Smoke Test | AU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
374000 | Receivables | Smoke Test | AU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
375000 | Receivables | Smoke Test | AW1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
376000 | Receivables | Smoke Test | AW2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
377000 | Receivables | Smoke Test | AW3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
378000 | Receivables | Smoke Test | AW4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
379000 | Receivables | Smoke Test | AC1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
380000 | Receivables | Smoke Test | AC2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
381000 | Receivables | Smoke Test | AC3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
382000 | Receivables | Smoke Test | AC4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
383000 | Receivables | Smoke Test | AC5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
384000 | Receivables | Smoke Test | AC6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
385000 | Receivables | Smoke Test | AC7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
386000 | Receivables | Smoke Test | AC8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
387000 | Receivables | Smoke Test | AB |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
388000 | Receivables | Smoke Test | AQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
389000 | Receivables | Smoke Test | AQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
390000 | Receivables | Smoke Test | AQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
391000 | Receivables | Smoke Test | AQ3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
392000 | Receivables | Smoke Test | AQ4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
393000 | Receivables | Smoke Test | AQ5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
394000 | Receivables | Smoke Test | AR1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
395000 | Receivables | Smoke Test | AR2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
396000 | Receivables | Smoke Test | AR3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
397000 | Receivables | Smoke Test | AR4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
398000 | Receivables | Smoke Test | AR5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
399000 | Receivables | Smoke Test | AR6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
400000 | Receivables | Smoke Test | AR7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
401000 | Receivables | Smoke Test | AR8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
402000 | Receivables | Smoke Test | AR9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
403000 | Receivables | Smoke Test | AR10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
404000 | Receivables | Smoke Test | AR11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
405000 | Receivables | Smoke Test | AR12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
406000 | Receivables | Smoke Test | AR13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
407000 | Receivables | Smoke Test | AR14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
408000 | Receivables | Smoke Test | AR15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
409000 | Receivables | Smoke Test | AR16 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
410000 | Receivables | Smoke Test | AL1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
411000 | Receivables | Smoke Test | AL2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
412000 | Receivables | Smoke Test | AL3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
413000 | Receivables | Smoke Test | AF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
414000 | Receivables | Smoke Test | AF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
415000 | Receivables | Smoke Test | AF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
416000 | Receivables | Smoke Test | AF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
417000 | Receivables | Smoke Test | AF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
418000 | Receivables | Smoke Test | AF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
419000 | Receivables | Smoke Test | AF7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
420000 | Receivables | Smoke Test | AF8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
421000 | Payables | Smoke Test | VU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
422000 | Payables | Smoke Test | VU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
423000 | Payables | Smoke Test | VU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
424000 | Payables | Smoke Test | AW1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
425000 | Payables | Smoke Test | AW2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
426000 | Payables | Smoke Test | VB1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
427000 | Payables | Smoke Test | VB2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
428000 | Payables | Smoke Test | VB3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
429000 | Payables | Smoke Test | VC1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
430000 | Payables | Smoke Test | VC2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
431000 | Payables | Smoke Test | VC3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
432000 | Payables | Smoke Test | VC4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
433000 | Payables | Smoke Test | VC5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
434000 | Payables | Smoke Test | VT1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
435000 | Payables | Smoke Test | VT2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
436000 | Payables | Smoke Test | VT3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
437000 | Payables | Smoke Test | VT4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
438000 | Payables | Smoke Test | VL1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
439000 | Payables | Smoke Test | VL2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
440000 | Payables | Smoke Test | VL3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
441000 | Payables | Smoke Test | VQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
442000 | Payables | Smoke Test | VQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
443000 | Payables | Smoke Test | VQ3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
444000 | Payables | Smoke Test | VQ4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
445000 | Payables | Report | VR1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
446000 | Payables | Report | VR2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
447000 | Payables | Report | VR3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
448000 | Payables | Report | VR4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
449000 | Payables | Report | VR5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
450000 | Payables | Report | VR6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
451000 | Payables | Report | VR7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
452000 | Payables | Report | VR8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
453000 | Payables | Report | VR9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
454000 | Payables | Report | VR10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
455000 | Payables | Report | VR11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
456000 | Payables | Report | VR12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
457000 | Payables | Report | VR13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
458000 | Payables | Report | VR14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
459000 | Payables | Report | VR15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
460000 | Payables | Smoke Test | VF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
461000 | Payables | Smoke Test | VF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
462000 | Payables | Smoke Test | VF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
463000 | Payables | Smoke Test | VF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
464000 | Payables | Smoke Test | VF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
465000 | Payables | Smoke Test | VF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
466000 | General Ledger | Smoke Test | GU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
467000 | General Ledger | Smoke Test | GU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
468000 | General Ledger | Smoke Test | GU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
469000 | General Ledger | Smoke Test | GU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
470000 | General Ledger | Smoke Test | GU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
471000 | General Ledger | Smoke Test | GC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
472000 | General Ledger | Smoke Test | GY |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
473000 | General Ledger | Smoke Test | GT |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
474000 | General Ledger | Smoke Test | GW1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
475000 | General Ledger | Smoke Test | GW2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
476000 | General Ledger | Smoke Test | GW3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
477000 | General Ledger | Smoke Test | GQ |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
478000 | General Ledger | Smoke Test | GR1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
479000 | General Ledger | Report | GR1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
| General Ledger | Report | GR2 |  | Launch without error message and review basic functionality |  | Passed |  | 2016-08-17
480000 | General Ledger | Report | GR3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
481000 | General Ledger | Report | GR4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
482000 | General Ledger | Report | GR5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
483000 | General Ledger | Report | GR6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
484000 | General Ledger | Report | GR7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
485000 | General Ledger | Report | GR8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
486000 | General Ledger | Report | GR9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
487000 | General Ledger | Smoke Test | GF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
488000 | General Ledger | Smoke Test | GF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
489000 | General Ledger | Smoke Test | GF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
490000 | General Ledger | Smoke Test | GF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
491000 | General Ledger | Smoke Test | GF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
492000 | General Ledger | Smoke Test | GF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
493000 | System | Smoke Test | NL1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
494000 | System | Smoke Test | NL2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
495000 | System | Smoke Test | NF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
496000 | System | Smoke Test | NF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
497000 | System | Smoke Test | NF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
498000 | System | Smoke Test | NF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
499000 | System | Smoke Test | NF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
500000 | System | Smoke Test | NF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
501000 | System | Smoke Test | NF7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
502000 | System | Smoke Test | NF8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
503000 | System | Smoke Test | NF9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
504000 | System | Smoke Test | BF10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
505000 | System | Smoke Test | NF11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
506000 | System | Smoke Test | NF12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
507000 | System | Smoke Test | NF13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
508000 | System | Smoke Test | NF14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
509000 | System | Smoke Test | NF15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
510000 | System | Smoke Test | NY1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
511000 | System | Smoke Test | NY2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
512000 | System | Smoke Test | NY3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
513000 | System | Smoke Test | NY4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
514000 | System | Smoke Test | NY5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
515000 | System | Smoke Test | NY6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
516000 | System | Smoke Test | NY7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
517000 | System | Smoke Test | NY8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
518000 | System | Smoke Test | NY9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
519000 | System | Smoke Test | NY10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
520000 | System | Smoke Test | NY11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
521000 | System | Smoke Test | NY12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
522000 | System | Smoke Test | NY13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
523000 | System | Smoke Test | NY14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
524000 | System | Smoke Test | NY15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
525000 | System | Smoke Test | NU |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
526000 | System | Smoke Test | NC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
527000 | System | Smoke Test | NB |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
528000 | System | Smoke Test | NK1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
529000 | System | Smoke Test | NK2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
530000 | System | Smoke Test | NK3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
| System | Smoke Test | NK4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
| System | Smoke Test | NK5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
531000 | System | Smoke Test | NR |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
532000 | System | Smoke Test | NT |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
533000 | System | Smoke Test | NQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
534000 | System | Smoke Test | NQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
535000 | System | Smoke Test | NQ3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
536000 | System | Smoke Test | NQ4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
537000 | System | Smoke Test | NQ5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
538000 | System | Smoke Test | NQ6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
539000 | System | Smoke Test | NQ7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
540000 | System | Smoke Test | NQ8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
541000 | System | Smoke Test | NQ9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
542000 | System | Smoke Test | NQ10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
543000 | System | Smoke Test | NQ11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
544000 | System | Smoke Test | NQ12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
545000 | System | Smoke Test | NQ13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
546000 | System | Smoke Test | NQ14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
547000 | System | Smoke Test | NQ15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
548000 | System | Smoke Test | NQ16 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
549000 | System | Smoke Test | NW |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-08-17
550000 | System | Smoke Test | NZ1 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-08-17
551000 | System | Smoke Test | NZ2 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-08-17
552000 | System | Smoke Test | NZ3 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-08-17
553000 | System | Smoke Test | NZ4 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-08-17
554000 | System | Smoke Test | NZ5 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-08-17
555000 | System | Smoke Test | NZ6 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-08-17
556000 | System | Smoke Test | NZ7 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-08-17
557000 | System | Smoke Test | NZ8 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-08-17
558000 | System | Smoke Test | NZ9 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-08-17
559000 | System | Smoke Test | NZ10 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-08-17
| System | Smoke Test | NZ11 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-08-17
| System | Smoke Test | NZ12 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-08-17
560000 | System | Smoke Test | NR1 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-08-17
561000 | System | Smoke Test | NR2 |  | Launch without error message and review basic functionality | 99 |  | John Loeb | 2016-08-17
562000 | System | Smoke Test | NR3 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-08-17
563000 | System | Smoke Test | NR4 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-08-17
564000 | System | Smoke Test | NR5 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-08-17
565000 | System | Smoke Test | Exit |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-08-17

## Test Scripts - Estimating
v Use this filter to find the test
Script ID | Test # | Step # | Action | Expected Result | Actual Result (blank if Expected Result met) | Passed?
102100-01 | 102100 | 1
102100-02 | 102100 | 2
102100-03 | 102100 | 3
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00

## Test Scripts - Order Processing
v Use this filter to find the test
Script ID | Test # | Step # | Action | Expected Result | Actual Result (blank if Expected Result met) | Passed?
102100-01 | 102100 | 1
102100-02 | 102100 | 2
102100-03 | 102100 | 3
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00

## Test Data
Data Type | Data ID | Data Description
Estimate |  | Existing Single Item Estimate - Corrugated
Estimate |  | Existing Set Estimate - Corrugated
Order
BOL
OE Invoice
AR Invoice
Release
Job