## Test Master
[6 empty] | Run | 99.02%
[6 empty] | Passed | 82.25%
[6 empty] | Failed | 17.75%
| Tests in this color have Scripts on another sheet ( use "Note" format at top) |  |  |  |  | Blocked | 0%
Test # | Category | Sub-category | Application | Time Speed | Test | Priority | Passed | Tester Name | Test Date | Failure Notes | Failure Task | Notes
101000 | Estimating | Smoke Test | EF |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Locking - REC Cnt:1 - layout, inks,
102000 | Estimating | Smoke Test | EF |  | Choose a record on first browser. Click through all tabs. Validate that there are no error messages. | 2 | Failed | John Loeb | 2016-07-20 | Locking - REC Cnt:1 - layout, inks,
102100 | Estimating | Add Estimate | EF |  | Add an estimate for a single item | 3 | Failed | John Loeb | 2016-07-20 | Locking when adding an Estimate (clicked on add button icon)
102200 | Estimating | Add Estimate | EF |  | Add an estimate for a tandem | 3 |  |  |  | locking and transaction - Red
102300 | Estimating | Add Estimate | EF |  | Add an estimate for a set | 3 |  |  |  | invalid or inapropriate handle (2128)
103000 | Estimating | Smoke Test | EC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
103100 | Estimating | Smoke Test | EC |  | Choose a record on first browser. Click through all tabs. Validate that there are no error messages. | 2 |  | John Loeb
103200 | Estimating | Add Estimate | EC |  | Add an estimate for a single item | 3 | Failed | John Loeb | 2016-07-20 | E-F- click on + icon add an new estimate - Invalid or inapropriate handle (2128)
103300 | Estimating | Add Estimate | EC |  | Add an estimate for a tandem | 3 | Failed | John Loeb | 2016-07-20 | locking and transaction - Red
103400 | Estimating | Add Estimate | EC |  | Add an estimate for a set | 3 | Failed | John Loeb | 2016-07-20 | invalid or inapropriate handle (2128)
|  |  | EQ |  | Quotes |  | Passed | John Loeb | 2016-07-20
|  |  | KY |  | Kopy Estime |  | Passed | John Loeb | 2016-07-20
|  |  | ES |  | Search for Estimates |  | Passed | John Loeb | 2016-07-20
|  |  | EG |  | Global Quote Price Change |  | Passed | John Loeb | 2016-07-20
|  |  | ET |  | Tools for Sales |  | Passed | John Loeb | 2016-07-20
|  |  | ER1 | passed | Control File |  | Passed | John Loeb | 2016-07-20
|  |  | ER2 | passed | machine File |  | Passed | John Loeb | 2016-07-20
|  |  | ER3 | passed | Style File |  | Passed | John Loeb | 2016-07-20
|  |  | ER4 | passed | Prep File |  | Passed | John Loeb | 2016-07-20
|  |  | ER5 | passed | Estimates List |  | Passed | John Loeb | 2016-07-20
|  |  | ER6 | passed | Quotes List |  | Passed | John Loeb | 2016-07-20
|  |  | ER7 | passed | prep List by Mat'l Type |  | Passed | John Loeb | 2016-07-20
|  |  | ER8 | passed | Estimate by Size |  | Passed | John Loeb | 2016-07-20
|  |  | ER9 | passed | Quoted price List |  | Passed | John Loeb | 2016-07-20
|  |  | ER10 | passed | Estimates List w/margins |  | Passed | John Loeb | 2016-07-20
|  |  | EB1 |  | Machine File |  | Failed | John Loeb | 2016-07-20 | Locking - brws mach
|  |  | EB2 |  | Folding Styles |  | Passed | John Loeb | 2016-07-20
|  |  | EB3 |  | Corrugated Styles |  | Passed | John Loeb | 2016-07-20
|  |  | EB4 |  | Box Design |  | Passed | John Loeb | 2016-07-20
|  |  | EB5 |  | Stacking Patterns |  | Passed | John Loeb | 2016-07-20
|  |  | EB6 |  | Stacking matrix |  | Passed | John Loeb | 2016-07-20
|  |  | EB7 |  | Flute Unit Counts |  | Passed | John Loeb | 2016-07-20
|  |  | EB8 |  | Prep and Die File |  | Passed | John Loeb | 2016-07-20
|  |  | EB9 |  | Cost Estimate Control |  | Failed | John Loeb | 2016-07-20
|  |  | EB10 |  | Truck / Common Carriers |  | Passed | John Loeb | 2016-07-20
|  |  | EB11 |  | Machine Routings |  | Passed | John Loeb | 2016-07-20
|  |  | EB12 |  | Score Types |  | Passed | John Loeb | 2016-07-20
|  |  | EB13 |  | machine Attachments / Adders |  | Passed | John Loeb | 2016-07-20
104000 | Order Processing | Smoke Test | OU1 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Locking - Release (prep/routing)
104100 | Order Processing | Smoke Test | OU1 |  | Choose a record on first browser. Click through all tabs. Validate that there are no error messages. | 2 | Failed | John Loeb | 2016-07-20 | locking - Release (prep/routing)
104200 | Order Processing | Add Order | OU1 |  | Add an order for a single item estimate. Validate that the order gets created with the correct information. | 3 | Failed | John Loeb | 2016-07-20 | Locking - Red
104300 | Order Processing | Add Order | OU1 |  | Add an order for 3 items. Validate that the order gets created with all three items with the correct information. | 3 | Failed | John Loeb | 2016-07-20 | Locking - Red
105000 | Order Processing | Smoke Test | OU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
106000 | Order Processing | Smoke Test | OU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
107000 | Order Processing | Smoke Test | OU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
108000 | Order Processing | Smoke Test | OU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
109000 | Order Processing | Smoke Test | OU6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
110000 | Order Processing | Smoke Test | OU7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
111000 | Order Processing | Smoke Test | OU8 |  | Launch without error message and review basic functionality | 99 | Failed | John Loeb | 2016-07-20 | Will not open
112000 | Order Processing | Smoke Test | OU9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
113000 | Order Processing | Smoke Test | OU10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
114000 | Order Processing | Smoke Test | OU11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
115000 | Order Processing | Smoke Test | OT1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
116000 | Order Processing | Smoke Test | OT2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
117000 | Order Processing | Smoke Test | OT3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
118000 | Order Processing | Smoke Test | OT4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
119000 | Order Processing | Smoke Test | OT5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
120000 | Order Processing | Smoke Test | OS1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
121000 | Order Processing | Smoke Test | OS2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
122000 | Order Processing | Smoke Test | OS3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
123000 | Order Processing | Smoke Test | OS4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
124000 | Order Processing | Smoke Test | OS5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
125000 | Order Processing | Smoke Test | OS6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
126000 | Order Processing | Smoke Test | OS7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
127000 | Order Processing | Smoke Test | OS8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
128000 | Order Processing | Smoke Test | OB1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
129000 | Order Processing | Smoke Test | OB2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
130000 | Order Processing | Smoke Test | OB3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
131000 | Order Processing | Smoke Test | OB4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
132000 | Order Processing | Smoke Test | OB5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
133000 | Order Processing | Smoke Test | OL1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
134000 | Order Processing | Smoke Test | OL2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
135000 | Order Processing | Smoke Test | OL3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
136000 | Order Processing | Smoke Test | OC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
137000 | Order Processing | Smoke Test | OW |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
138000 | Order Processing | Smoke Test | OQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
139000 | Order Processing | Smoke Test | OQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
140000 | Order Processing | Smoke Test | OQ3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
141000 | Order Processing | Smoke Test | OR1 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
142000 | Order Processing | Smoke Test | OR2 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
143000 | Order Processing | Smoke Test | OR3 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
144000 | Order Processing | Smoke Test | OR4 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
145000 | Order Processing | Smoke Test | OR5 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
146000 | Order Processing | Smoke Test | OR6 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
147000 | Order Processing | Smoke Test | OR7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
148000 | Order Processing | Smoke Test | OR8 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
149000 | Order Processing | Smoke Test | OR9 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
150000 | Order Processing | Smoke Test | OR10 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
151000 | Order Processing | Smoke Test | OR11 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
152000 | Order Processing | Smoke Test | OR12 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
153000 | Order Processing | Smoke Test | OR13 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
154000 | Order Processing | Smoke Test | OR14 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
155000 | Order Processing | Smoke Test | OR15 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
156000 | Order Processing | Smoke Test | OR16 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
157000 | Order Processing | Smoke Test | OZ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
158000 | Order Processing | Smoke Test | OZ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
159000 | Order Processing | Smoke Test | OZ3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
160000 | Order Processing | Smoke Test | OZ4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
161000 | Order Processing | Smoke Test | OZ5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
162000 | Order Processing | Smoke Test | OZ6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
163000 | Order Processing | Smoke Test | OZ7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
164000 | Order Processing | Smoke Test | OZ8 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Locking - Red
165000 | Order Processing | Smoke Test | OZ9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
166000 | Order Processing | Smoke Test | OF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
167000 | Order Processing | Smoke Test | OF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
168000 | Order Processing | Smoke Test | OF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
169000 | Order Processing | Smoke Test | OF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
170000 | Order Processing | Smoke Test | OF5 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | locking - red
171000 | Order Processing | Smoke Test | OF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
172000 | Order Processing | Smoke Test | OF7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
173000 | Order Processing | Smoke Test | OF8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
174000 | Order Processing | Smoke Test | OF9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
175000 | Raw Materials | Smoke Test | MU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
176000 | Raw Materials | Smoke Test | MU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
177000 | Raw Materials | Smoke Test | MU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
178000 | Raw Materials | Smoke Test | MU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
179000 | Raw Materials | Smoke Test | MU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
180000 | Raw Materials | Smoke Test | MU6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
181000 | Raw Materials | Smoke Test | MU7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
182000 | Raw Materials | Smoke Test | MU8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
183000 | Raw Materials | Smoke Test | MC1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
184000 | Raw Materials | Smoke Test | MC2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
185000 | Raw Materials | Smoke Test | MC3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
186000 | Raw Materials | Smoke Test | MG |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
187000 | Raw Materials | Smoke Test | MQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
188000 | Raw Materials | Smoke Test | MQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
189000 | Raw Materials | Smoke Test | MR1 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
190000 | Raw Materials | Smoke Test | MR2 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
191000 | Raw Materials | Smoke Test | MR3 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
192000 | Raw Materials | Smoke Test | MR4 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
193000 | Raw Materials | Smoke Test | MR5 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
194000 | Raw Materials | Smoke Test | MR6 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
195000 | Raw Materials | Smoke Test | MR7 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
196000 | Raw Materials | Smoke Test | MR8 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
197000 | Raw Materials | Smoke Test | MR9 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
198000 | Raw Materials | Smoke Test | MR10 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
199000 | Raw Materials | Smoke Test | MR11 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
200000 | Raw Materials | Smoke Test | MR12 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
201000 | Raw Materials | Smoke Test | MR13 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
202000 | Raw Materials | Smoke Test | MR14 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
203000 | Raw Materials | Smoke Test | MF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
204000 | Raw Materials | Smoke Test | MF2 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Locking - Red (bom) - Bin
205000 | Raw Materials | Smoke Test | MF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
206000 | Raw Materials | Smoke Test | MF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
207000 | Raw Materials | Smoke Test | MF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
208000 | Raw Materials | Smoke Test | MF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
209000 | Finished Goods | Smoke Test | IU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
210000 | Finished Goods | Smoke Test | IU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
211000 | Finished Goods | Smoke Test | IU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
212000 | Finished Goods | Smoke Test | IU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
213000 | Finished Goods | Smoke Test | IU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
214000 | Finished Goods | Smoke Test | IU6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
215000 | Finished Goods | Smoke Test | IU7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
216000 | Finished Goods | Smoke Test | IU8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
217000 | Finished Goods | Smoke Test | IU9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
218000 | Finished Goods | Smoke Test | IC1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
219000 | Finished Goods | Smoke Test | IC2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
220000 | Finished Goods | Smoke Test | IC3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
221000 | Finished Goods | Smoke Test | IW |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
222000 | Finished Goods | Smoke Test | IQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
223000 | Finished Goods | Smoke Test | IQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
224000 | Finished Goods | Smoke Test | IR1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
225000 | Finished Goods | Smoke Test | IR2 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
226000 | Finished Goods | Smoke Test | IR3 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
227000 | Finished Goods | Smoke Test | IR4 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
228000 | Finished Goods | Smoke Test | IR5 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
229000 | Finished Goods | Smoke Test | IR6 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
230000 | Finished Goods | Smoke Test | IR7 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
231000 | Finished Goods | Smoke Test | IR8 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
232000 | Finished Goods | Smoke Test | IR9 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
233000 | Finished Goods | Smoke Test | IR10 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
234000 | Finished Goods | Smoke Test | IR11 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
235000 | Finished Goods | Smoke Test | IR12 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
236000 | Finished Goods | Smoke Test | IR13 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
237000 | Finished Goods | Smoke Test | IR14 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
238000 | Finished Goods | Smoke Test | IR15 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
239000 | Finished Goods | Smoke Test | IL1 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
240000 | Finished Goods | Smoke Test | IL2 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
241000 | Finished Goods | Smoke Test | IL3 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
242000 | Finished Goods | Smoke Test | IL4 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
243000 | Finished Goods | Smoke Test | IL5 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
244000 | Finished Goods | Smoke Test | IL6 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
245000 | Finished Goods | Smoke Test | IL7 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
246000 | Finished Goods | Smoke Test | IL8 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
247000 | Finished Goods | Smoke Test | IL9 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
248000 | Finished Goods | Smoke Test | IL10 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
249000 | Finished Goods | Smoke Test | IL11 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
250000 | Finished Goods | Smoke Test | IL12 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
251000 | Finished Goods | Smoke Test | IL13 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
252000 | Finished Goods | Smoke Test | IL14 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
253000 | Finished Goods | Smoke Test | IL15 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
254000 | Finished Goods | Smoke Test | IF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
255000 | Finished Goods | Smoke Test | IF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
256000 | Finished Goods | Smoke Test | IF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
257000 | Finished Goods | Smoke Test | IF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
258000 | Finished Goods | Smoke Test | IF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
259000 | Finished Goods | Smoke Test | IF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
260000 | Finished Goods | Smoke Test | IF7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
261000 | Sales Reports | Smoke Test | HC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
262000 | Sales Reports | Smoke Test | HB |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
263000 | Sales Reports | Smoke Test | HF |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
264000 | Sales Reports | Smoke Test | HT |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
265000 | Sales Reports | Smoke Test | HW |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
266000 | Sales Reports | Smoke Test | HZ |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
267000 | Sales Reports | Smoke Test | HV |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
268000 | Sales Reports | Smoke Test | HY |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
269000 | Sales Reports | Smoke Test | HL |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
270000 | Sales Reports | Smoke Test | HS |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
271000 | Sales Reports | Smoke Test | HM1 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
| Sales Reports | Smoke Test | HM2 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
| Sales Reports | Smoke Test | HM3 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
| Sales Reports | Smoke Test | HM4 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
| Sales Reports | Smoke Test | HM5 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
|  |  | HM6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
272000 | Sales Reports | Smoke Test | HR1 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
273000 | Sales Reports | Smoke Test | HR2 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
274000 | Sales Reports | Smoke Test | HR3 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
275000 | Sales Reports | Smoke Test | HR4 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
276000 | Sales Reports | Smoke Test | HR5 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
277000 | Sales Reports | Smoke Test | HR6 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
278000 | Sales Reports | Smoke Test | HR7 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
279000 | Sales Reports | Smoke Test | HR8 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
280000 | Sales Reports | Smoke Test | HR9 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
281000 | Sales Reports | Smoke Test | HR10 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
282000 | Sales Reports | Smoke Test | HR11 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
283000 | Sales Reports | Smoke Test | HR12 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
284000 | Sales Reports | Smoke Test | HR13 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
285000 | Sales Reports | Smoke Test | HR14 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
286000 | Sales Reports | Smoke Test | HR15 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
287000 | Sales Reports | Smoke Test | HR16 | passed | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
288000 | Data Collection | Smoke Test | DU |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
289000 | Data Collection | Smoke Test | DF |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
290000 | Data Collection | Smoke Test | DL1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
291000 | Data Collection | Smoke Test | DL2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
292000 | Data Collection | Smoke Test | DL3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
293000 | Data Collection | Smoke Test | DW |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
294000 | Data Collection | Smoke Test | DT |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
295000 | Data Collection | Smoke Test | DQ1 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Error loading image ico
296000 | Data Collection | Smoke Test | DR1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
297000 | Data Collection | Smoke Test | DR2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
298000 | Data Collection | Smoke Test | DR3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
299000 | Data Collection | Smoke Test | DR4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
300000 | Data Collection | Smoke Test | DR5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
301000 | Data Collection | Smoke Test | DR6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
302000 | Data Collection | Smoke Test | DR7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
303000 | Data Collection | Smoke Test | DR8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
304000 | Data Collection | Smoke Test | DR9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
305000 | Data Collection | Smoke Test | DR10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
306000 | Data Collection | Smoke Test | DR11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
307000 | Data Collection | Smoke Test | DR12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
308000 | Data Collection | Smoke Test | DR13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
309000 | Data Collection | Smoke Test | DR14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
310000 | Data Collection | Smoke Test | DR15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
311000 | Data Collection | Smoke Test | DE1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
312000 | Jobs | Smoke Test | JU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
313000 | Jobs | Smoke Test | JU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
314000 | Jobs | Smoke Test | JU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
315000 | Jobs | Smoke Test | JU4 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
316000 | Jobs | Smoke Test | JU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
317000 | Jobs | Smoke Test | JU6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
319000 | Jobs | Smoke Test | JU7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
320000 | Jobs | Smoke Test | JU8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
321000 | Jobs | Smoke Test | JC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
322000 | Jobs | Smoke Test | JQ1 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Error loading image ico
323000 | Jobs | Smoke Test | JR1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
324000 | Jobs | Smoke Test | JR2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
325000 | Jobs | Smoke Test | JR3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
326000 | Jobs | Smoke Test | JR4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
327000 | Jobs | Smoke Test | JR5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
328000 | Jobs | Smoke Test | JR6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
329000 | Jobs | Smoke Test | JR7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
330000 | Jobs | Smoke Test | JR8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
331000 | Jobs | Smoke Test | JR9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
332000 | Jobs | Smoke Test | JR10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
333000 | Jobs | Smoke Test | JR11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
334000 | Jobs | Smoke Test | JR12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
335000 | Jobs | Smoke Test | JR13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
336000 | Jobs | Smoke Test | JR14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
337000 | Jobs | Smoke Test | JR15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
338000 | Jobs | Smoke Test | JL1 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
339000 | Jobs | Smoke Test | JL2 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
340000 | Jobs | Smoke Test | JL3 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
341000 | Jobs | Smoke Test | JL4 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
342000 | Jobs | Smoke Test | JL5 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
343000 | Jobs | Smoke Test | JL6 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
344000 | Jobs | Smoke Test | JL7 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
345000 | Jobs | Smoke Test | JF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
346000 | Jobs | Smoke Test | JF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
347000 | Jobs | Smoke Test | JF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
348000 | Jobs | Smoke Test | JF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
349000 | Jobs | Smoke Test | JF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
350000 | Scheduler | Smoke Test | S3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20 |  | 16286
|  | Smoke Test | PU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
|  | Smoke Test | PU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
351000 | Purchasing | Smoke Test | PU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
352000 | Purchasing | Smoke Test | Pu4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
353000 | Purchasing | Smoke Test | PQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
354000 | Purchasing | Smoke Test | PR1 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
355000 | Purchasing | Smoke Test | PR2 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
356000 | Purchasing | Smoke Test | PR3 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
357000 | Purchasing | Smoke Test | PR4 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
358000 | Purchasing | Smoke Test | PR5 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
359000 | Purchasing | Smoke Test | PR6 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
360000 | Purchasing | Smoke Test | PR7 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
361000 | Purchasing | Smoke Test | PR8 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
362000 | Purchasing | Smoke Test | PR9 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
363000 | Purchasing | Smoke Test | PR10 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
364000 | Purchasing | Smoke Test | PR11 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
365000 | Purchasing | Smoke Test | PR12 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
366000 | Purchasing | Smoke Test | PR13 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
367000 | Purchasing | Smoke Test | PR14 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
368000 | Purchasing | Smoke Test | PF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
369000 | Purchasing | Smoke Test | PF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
370000 | Receivables | Smoke Test | AU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
371000 | Receivables | Smoke Test | AU2 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
372000 | Receivables | Smoke Test | AU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
373000 | Receivables | Smoke Test | AU4 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
374000 | Receivables | Smoke Test | AU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
375000 | Receivables | Smoke Test | AW1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
376000 | Receivables | Smoke Test | AW2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
377000 | Receivables | Smoke Test | AW3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
378000 | Receivables | Smoke Test | AW4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
379000 | Receivables | Smoke Test | AC1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
380000 | Receivables | Smoke Test | AC2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
381000 | Receivables | Smoke Test | AC3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
382000 | Receivables | Smoke Test | AC4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
383000 | Receivables | Smoke Test | AC5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
384000 | Receivables | Smoke Test | AC6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
385000 | Receivables | Smoke Test | AC7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
386000 | Receivables | Smoke Test | AC8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
387000 | Receivables | Smoke Test | AB |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
388000 | Receivables | Smoke Test | AQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
389000 | Receivables | Smoke Test | AQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
390000 | Receivables | Smoke Test | AQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
391000 | Receivables | Smoke Test | AQ3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
392000 | Receivables | Smoke Test | AQ4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
393000 | Receivables | Smoke Test | AQ5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
394000 | Receivables | Smoke Test | AR1 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Transaction - Red
395000 | Receivables | Smoke Test | AR2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
396000 | Receivables | Smoke Test | AR3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
397000 | Receivables | Smoke Test | AR4 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
398000 | Receivables | Smoke Test | AR5 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
399000 | Receivables | Smoke Test | AR6 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
400000 | Receivables | Smoke Test | AR7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
401000 | Receivables | Smoke Test | AR8 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
402000 | Receivables | Smoke Test | AR9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
403000 | Receivables | Smoke Test | AR10 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
404000 | Receivables | Smoke Test | AR11 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
405000 | Receivables | Smoke Test | AR12 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
406000 | Receivables | Smoke Test | AR13 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
407000 | Receivables | Smoke Test | AR14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
408000 | Receivables | Smoke Test | AR15 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
409000 | Receivables | Smoke Test | AR16 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
410000 | Receivables | Smoke Test | AL1 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
411000 | Receivables | Smoke Test | AL2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
412000 | Receivables | Smoke Test | AL3 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
413000 | Receivables | Smoke Test | AF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
414000 | Receivables | Smoke Test | AF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
415000 | Receivables | Smoke Test | AF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
416000 | Receivables | Smoke Test | AF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
417000 | Receivables | Smoke Test | AF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
418000 | Receivables | Smoke Test | AF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
419000 | Receivables | Smoke Test | AF7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
420000 | Receivables | Smoke Test | AF8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
421000 | Payables | Smoke Test | VU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
422000 | Payables | Smoke Test | VU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
423000 | Payables | Smoke Test | VU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
424000 | Payables | Smoke Test | AW1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
425000 | Payables | Smoke Test | AW2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
426000 | Payables | Smoke Test | VB1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
427000 | Payables | Smoke Test | VB2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
428000 | Payables | Smoke Test | VB3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
429000 | Payables | Smoke Test | VC1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
430000 | Payables | Smoke Test | VC2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
431000 | Payables | Smoke Test | VC3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
432000 | Payables | Smoke Test | VC4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
433000 | Payables | Smoke Test | VC5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
434000 | Payables | Smoke Test | VT1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
435000 | Payables | Smoke Test | VT2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
436000 | Payables | Smoke Test | VT3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
437000 | Payables | Smoke Test | VT4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
438000 | Payables | Smoke Test | VL1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
439000 | Payables | Smoke Test | VL2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
440000 | Payables | Smoke Test | VL3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
441000 | Payables | Smoke Test | VQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
442000 | Payables | Smoke Test | VQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
443000 | Payables | Smoke Test | VQ3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
444000 | Payables | Smoke Test | VQ4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
445000 | Payables | Smoke Test | VR1 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
446000 | Payables | Smoke Test | VR2 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
447000 | Payables | Smoke Test | VR3 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
448000 | Payables | Smoke Test | VR4 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
449000 | Payables | Smoke Test | VR5 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
450000 | Payables | Smoke Test | VR6 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
451000 | Payables | Smoke Test | VR7 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
452000 | Payables | Smoke Test | VR8 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
453000 | Payables | Smoke Test | VR9 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
454000 | Payables | Smoke Test | VR10 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
455000 | Payables | Smoke Test | VR11 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
456000 | Payables | Smoke Test | VR12 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
457000 | Payables | Smoke Test | VR13 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
458000 | Payables | Smoke Test | VR14 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
459000 | Payables | Smoke Test | VR15 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
460000 | Payables | Smoke Test | VF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
461000 | Payables | Smoke Test | VF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
462000 | Payables | Smoke Test | VF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
463000 | Payables | Smoke Test | VF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
464000 | Payables | Smoke Test | VF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
465000 | Payables | Smoke Test | VF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
466000 | General Ledger | Smoke Test | GU1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
467000 | General Ledger | Smoke Test | GU2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
468000 | General Ledger | Smoke Test | GU3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
469000 | General Ledger | Smoke Test | GU4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
470000 | General Ledger | Smoke Test | GU5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
471000 | General Ledger | Smoke Test | GC |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
472000 | General Ledger | Smoke Test | GY |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
473000 | General Ledger | Smoke Test | GT |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
474000 | General Ledger | Smoke Test | GW1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
475000 | General Ledger | Smoke Test | GW2 |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20 | Locking - red (Detail)
476000 | General Ledger | Smoke Test | GW3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
477000 | General Ledger | Smoke Test | GQ |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
478000 | General Ledger | Smoke Test | GR1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
479000 | General Ledger | Smoke Test | GR1 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
| General Ledger | Smoke Test | GR2 | passed | Launch without error message and review basic functionality
480000 | General Ledger | Smoke Test | GR3 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
481000 | General Ledger | Smoke Test | GR4 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
482000 | General Ledger | Smoke Test | GR5 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
483000 | General Ledger | Smoke Test | GR6 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
484000 | General Ledger | Smoke Test | GR7 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
485000 | General Ledger | Smoke Test | GR8 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
486000 | General Ledger | Smoke Test | GR9 | passed | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
487000 | General Ledger | Smoke Test | GF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
488000 | General Ledger | Smoke Test | GF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
489000 | General Ledger | Smoke Test | GF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
490000 | General Ledger | Smoke Test | GF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
491000 | General Ledger | Smoke Test | GF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
492000 | General Ledger | Smoke Test | GF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
493000 | System | Smoke Test | NL1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
494000 | System | Smoke Test | NL2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
495000 | System | Smoke Test | NF1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
496000 | System | Smoke Test | NF2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
497000 | System | Smoke Test | NF3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
498000 | System | Smoke Test | NF4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
499000 | System | Smoke Test | NF5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
500000 | System | Smoke Test | NF6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
501000 | System | Smoke Test | NF7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
502000 | System | Smoke Test | NF8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
503000 | System | Smoke Test | NF9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
504000 | System | Smoke Test | BF10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
505000 | System | Smoke Test | NF11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
506000 | System | Smoke Test | NF12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
507000 | System | Smoke Test | NF13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
508000 | System | Smoke Test | NF14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
509000 | System | Smoke Test | NF15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
510000 | System | Smoke Test | NY1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
511000 | System | Smoke Test | NY2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
512000 | System | Smoke Test | NY3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
513000 | System | Smoke Test | NY4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
514000 | System | Smoke Test | NY5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
515000 | System | Smoke Test | NY6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
516000 | System | Smoke Test | NY7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
517000 | System | Smoke Test | NY8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
518000 | System | Smoke Test | NY9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
519000 | System | Smoke Test | NY10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
520000 | System | Smoke Test | NY11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
521000 | System | Smoke Test | NY12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
522000 | System | Smoke Test | NY13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
523000 | System | Smoke Test | NY14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
524000 | System | Smoke Test | NY15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
525000 | System | Smoke Test | NU |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
526000 | System | Smoke Test | NC |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
527000 | System | Smoke Test | NB |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
528000 | System | Smoke Test | NK1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
529000 | System | Smoke Test | NK2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
530000 | System | Smoke Test | NK3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
|  |  | NK4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
|  |  | NK5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
531000 | System | Smoke Test | NR |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
532000 | System | Smoke Test | NT |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
533000 | System | Smoke Test | NQ1 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
534000 | System | Smoke Test | NQ2 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
535000 | System | Smoke Test | NQ3 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
536000 | System | Smoke Test | NQ4 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
537000 | System | Smoke Test | NQ5 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
538000 | System | Smoke Test | NQ6 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
539000 | System | Smoke Test | NQ7 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
540000 | System | Smoke Test | NQ8 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
541000 | System | Smoke Test | NQ9 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
542000 | System | Smoke Test | NQ10 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
543000 | System | Smoke Test | NQ11 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
544000 | System | Smoke Test | NQ12 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
545000 | System | Smoke Test | NQ13 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
546000 | System | Smoke Test | NQ14 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
547000 | System | Smoke Test | NQ15 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
548000 | System | Smoke Test | NQ16 |  | Launch without error message and review basic functionality | 1 | Passed | John Loeb | 2016-07-20
549000 | System | Smoke Test | NW |  | Launch without error message and review basic functionality | 1 | Failed | John Loeb | 2016-07-20
550000 | System | Smoke Test | NZ1 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-07-20
551000 | System | Smoke Test | NZ2 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-07-20
552000 | System | Smoke Test | NZ3 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-07-20
553000 | System | Smoke Test | NZ4 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-07-20
554000 | System | Smoke Test | NZ5 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-07-20
555000 | System | Smoke Test | NZ6 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-07-20
556000 | System | Smoke Test | NZ7 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-07-20
557000 | System | Smoke Test | NZ8 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-07-20
558000 | System | Smoke Test | NZ9 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-07-20
559000 | System | Smoke Test | NZ10 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-07-20
560000 | System | Smoke Test | NR1 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-07-20
561000 | System | Smoke Test | NR2 |  | Launch without error message and review basic functionality | 99 |  | John Loeb | 2016-07-20
562000 | System | Smoke Test | NR3 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-07-20
563000 | System | Smoke Test | NR4 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-07-20
564000 | System | Smoke Test | NR5 |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-07-20
565000 | System | Smoke Test | Exit |  | Launch without error message and review basic functionality | 2 | Passed | John Loeb | 2016-07-20

## Test Scripts - Estimating
v Use this filter to find the test
Script ID | Test # | Step # | Action | Expected Result | Actual Result (blank if Expected Result met) | Passed?
102100-01 | 102100 | 1
102100-02 | 102100 | 2
102100-03 | 102100 | 3
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00

## Test Scripts - Order Processing
v Use this filter to find the test
Script ID | Test # | Step # | Action | Expected Result | Actual Result (blank if Expected Result met) | Passed?
102100-01 | 102100 | 1
102100-02 | 102100 | 2
102100-03 | 102100 | 3
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00
-00

## Test Data
Data Type | Data ID | Data Description
Estimate |  | Existing Single Item Estimate - Corrugated
Estimate |  | Existing Set Estimate - Corrugated
Order
BOL
OE Invoice
AR Invoice
Release
Job